## Metadata
Reporting Round | Fund Name
2v2 | Pathfinders

## Start
Pathfinders Reporting Template
PF-USER_CURRENT-REPORTING-PERIOD-START
Reporting period
Q2 2024/25: Jul 2024 - Sep 2024
PF-USER_CURRENT-REPORTING-PERIOD-END
Sections in this template
Admin
Provide key dates, the name of your organisation, and contact details.
Progress
Provide the information on the delivery of your portfolio which include spend and delivery RAG ratings for each project, issues, and key upcoming milestones.
Project location
Provide the postcode or postcodes associated with each project.
Outputs
Provide outputs for various intervention themes. Standard and bespoke outputs are supported.
Outcomes
Provide outcomes for various intervention themes. Standard and bespoke outcomes are supported.
Finances
Provide committed and forecast spend at both portfolio and project level, and plans for uncommitted funding, or underspend.
Risks
List the top five risks across your portfolio and their mitigations.
Sign off
Section 151 Officer or Chief Finance Officer to sign off the template before submission.
Reporting Period
<Select>
April 2023 to Sept 2023
Oct 2023 to March 2024
April 2024 to Sept 2024
Sept 2024 to Feb 2025

## Admin
Admin
PF-USER_FINANCIAL-COMPLETION-DATE-START
Financial completion date
Date by which portfolio grant funding will be defrayed by Local Authority.
2026-12-31
PF-USER_FINANCIAL-COMPLETION-DATE-END
PF-USER_ACTIVITY-END-DATE-START
Activity end date
Date by which all of the physical project activity will be completed.
ef
PF-USER_ACTIVITY-END-DATE-END
PF-USER_PRACTICAL-COMPLETION-DATE-START
Practical completion date
Date by which Pathfinder grant elements of projects will be physically complete and all Pathfinder portfolio outputs achieved.
2027-04-01
PF-USER_PRACTICAL-COMPLETION-DATE-END
PF-USER_ORGANISATION-NAME-START
Organisation name | Fund Type 1 | Place Name A
Bolton Council
PF-USER_ORGANISATION-NAME-END
Who is the best person to contact about this return?
PF-USER_CONTACT-NAME-START
Contact name
Me
PF-USER_CONTACT-NAME-END
PF-USER_CONTACT-EMAIL-START
Contact email | Fund Type 3 | Place Name C
me@me.com
PF-USER_CONTACT-EMAIL-END
PF-USER_CONTACT-TELEPHONE-START
Contact telephone | Fund Type 4 | Place Name D
This field is optional
01234 55667712
PF-USER_CONTACT-TELEPHONE-END |  | Place Name F
Place Name G
Place Name H
Place Name I
Place Name J
Place Name K
Place Name L
Place Name M
Place Name N
Place Name O
Place Name P
Place Name Q
Place Name R

## Progress
Progress
Portfolio level RAG rating
Please provide overall RAG ratings for your portfolio-level spend and delivery.
PF-USER_PORTFOLIO-RAG-RATINGS-START | PF-USER_PORTFOLIO-RAG-RATING-START | PF-USER_PORTFOLIO-RAG-RATING-START | PF-USER_PORTFOLIO-RAG-RATING-START
Statement |  |  | RAG rating
Your ability to spend the current spending profile |  |  | Amber/Green
Your current portfolio-level delivery progress |  |  | Please select an option
PF-USER_PORTFOLIO-PROGRESS-START |  |  |  | PF-USER_PORTFOLIO-RAG-RATINGS-END
Portfolio progress
How is the delivery of your portfolio progressing? • Please provide a portfolio-level summary of the last financial quarter, together with more detailed updates on individual projects as required. This could be where a greater level of progress has been made, or challenges have affected delivery and/or defrayal of Pathfinder funds, particularly where holistic delivery is concerned, i.e. projects are contingent on others meeting milestones etc. • For projects where RAG ratings have increased since the previous monitoring return, we expect to see additional narrative to provide clarity and justification. • For significant challenges on projects across the portfolio, please utilise the section below on big issues across portfolio to provide further detail.
Very well, thank you.
500 words suggested |  |  |  | PF-USER_PORTFOLIO-PROGRESS-END
Project progress
Spend Risk |  |  |  | Delivery Risk
The table below is for illustrative guidance purposes only and the examples given are not intended to cover all potiential project scenarios. It is not an exhaustive list and only intended as a prompt for some of the things you might consider when RAG (red, amber, green) scoring the spend and delivery risks associated with your individual projects. You should rate each project based on your own knowledge of the individual circumstances influencing both spend and delivery risk. Use the narrative box to provide further explanation.
Enter a spend RAG rating for each project and some explanatory narrative so we understand where you might need some support. To help you choose a rating, examples of what each rating might include are below. Green: no rising costs, no slippage, less than 30% expenditure profiled in final year, no use of financial flexibility. Amber/Green: project progressing but with minor issues identified, issues are within control of LA and there is a mitigation plan in place, the appropriate RIBA stage has minor slippage but a mitigation plan is in place, there is no additional support required. Amber: cost increases (10 to 20%) which are manageable, a funding gap exists but a source has been identified although not secured, there is slippage between 20% to 30% between financial years, 40% to 50% of expenditure is profiled in final year, the use of financial flexibilities is required but below threshold. Amber/Red: the project has stalled for any reason, Value Engineering is required or in progress due to significant cost increases or over-runs, significant additional match funding required to facilitate delivery, potential match funding source identified but not secured. Red: major cost increases over 30% which is un-manageable and there is no plan in place to resolve the problem, there is major slippage over 40% between financial years, over 60% of expenditure is profiled in final year, major movement of funding planned, major additional match funding required to facilitate delivery, match funding source not identified, call in required. |  |  |  | Enter a delivery RAG rating for each project and some explanatory narrative. This tells us where you might need support, and where we can celebrate success. Green: planning is in place, main contract procurement process complete, delivery milestones on target, appropriate RIBA stage on track, project completed. Amber/Green: project is progressing but minor issues identified (these are within control of LA and there is a plan in place), the appropriate RIBA stage has minor slippage but there is a plan in place to deal with the issue, no additional support required. Amber: the project progressing but delayed, the issues identified are within control of LA but there is currently no plan in place to deal with the issue, Value Engineering is required or in progress, the appropriate RIBA stage has slipped considerably, additional support required. Amber/Red: the project has stalled, Value Engineering is required or in progress and likely to result in a new planning application and delayed delivery timelines, major RIBA stage slippage, major additional support required. Red: project stalled, issues out of LA control, major support required, major RIBA stage slippage, no plan in place.
PF-USER_PROJECT-PROGRESS-START
Project name | Project status | Spend RAG rating | Delivery RAG rating | Why have you given these ratings? Enter an explanation (100 words max)
Please select an option
PF-BOL-001: Wellsprings Innovation Hub | In progress | Green | Red | Made
PF-BOL-002: Bolton Market Upgrades | In progress | Amber/Green | Green | Them
PF-BOL-003: Bolton Library & Museum Upgrade | Not started | Amber | Amber/Green | Up
PF-BOL-004: Public Realm Improvements | On hold | Amber/Red | Amber
PF-BOL-005: Accelerated Funding £1 million Public Realm Improvements | In progress | Red | Amber/Red | This
PF-BOL-006: Farnworth Market Precinct | In progress | Green | Red | Is
PF-BOL-007: Farnworth Leisure Centre Expansion | Project complete | Amber/Green | Green | My
PF-BOL-008: Streets for All - Farnworth | Project cancelled | Amber | Amber/Green | Test
PF-BOL-009: Bolton College of Medical Science | In progress | Amber/Red | Amber | Data
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
PF-USER_PROJECT-PROGRESS-END
PF-USER_BIG-ISSUES-ACROSS-PORTFOLIO-START
Big issues across portfolio
Tell us about the issues affecting delivery of your projects. We use this information to see how we might be able to help. • Expand on any spend/delivery issues highlighted in the above sections providing a rationale for how the issue(s) has materialised. Please include what stage delivery is at, what action is being taken to mitigate the issue(s) and estimated resolution date (if possible). You should also include how this will affect individual project milestones, including the March 2026 deadline set out in your MoU. You should justify/explain any need to reprofile any costs, outputs and outcomes into 26/27. • Please indicate whether a PAR is/will be required. • Where there is a variance on the Outputs and Outcomes tabs between the baseline data and the MR data, please include narrative in this section for the variance.
No Big Issues or any other magazines for that matter.
500 words suggested |  |  |  | PF-USER_BIG-ISSUES-ACROSS-PORTFOLIO-END
PF-USER_UPCOMING-SIGNIFICANT-MILESTONES-START
Upcoming significant milestones
What significant milestones are coming up? We use this information to find communication opportunities. For example, we might highlight your successes to others, write about them in a case study, or organise a ministerial visit.
Well Christmas is not very far away. That's quite significant for some people.
500 words suggested |  |  |  | PF-USER_UPCOMING-SIGNIFICANT-MILESTONES-END

## Project location
Project location
PF-USER_PROJECT-LOCATION-START
Project name | Project full postcode/postcodes (for example, AB1D 2EF)
If a project has multiple postcodes, enter postcodes with a comma separating each one (for example, AB1D 2EF, WC1 3RJ).
PF-BOL-001: Wellsprings Innovation Hub | BB8 9EE
PF-BOL-002: Bolton Market Upgrades | FY6 7YR
PF-BOL-003: Bolton Library & Museum Upgrade | BB8 9EE, FY6 7YR
PF-BOL-004: Public Realm Improvements | BB8 9EE
PF-BOL-005: Accelerated Funding £1 million Public Realm Improvements | FY6 7YR:X?..,; ∂
PF-BOL-006: Farnworth Market Precinct | BB8 9EE, FY6 7YR, FY3 7EY
PF-BOL-007: Farnworth Leisure Centre Expansion | BB8 9EE
PF-BOL-008: Streets for All - Farnworth | FY6 7YR
PF-BOL-009: Bolton College of Medical Science | FY3 7EY
PF-USER_PROJECT-LOCATION-END

## Outputs
Outputs
What have you delivered, and what is forecast to be delivered?
Tell us about the outputs you are delivering and the outcomes these are achieving, or expected to achieve. Provide this at portfolio level by intervention theme. Investment themes have been developed to help MHCLG evaluate how our funds are helping to achieve Levelling Up. Investment themes are designed to organise outputs and outcomes by the objective of the project rather than the nature of the activities being undertaken. This is because similar projects can have different objectives and different activities can achieve the same result. For example, road improvements can facilitate development by linking a site to the road network or strengthen the service economy by making it easier to access a visitor attraction. When selecting an investment theme, think about the main long term objective of delivering the output or outcome.
Description of investment themes
Intervention theme | Description
Improving quality of life for residents | Projects where the principal aim is to improve the quality of life of residents by improving the quality of local public services and associated infrastructure. Projects funded under this heading are diverse: including improvements to educational, health, leisure and community facilities, environmental amenities (for example, parks), investments in new or improved social housing stock, and provisioning of cycling and walking infrastructure.
Strengthening the local service economy | Projects aiming to support economic regeneration via stimulating greater levels of consumer spending in local economies. These include investments in culture or heritage assets that serve as visitor attractions, investments in the public realm (for example, town centre improvement projects or enhancements to other infrastructure to improve the visitor experience), and provisioning of new or improved retail floorspace.
Unlocking commercial, industrial and residential development | Projects aiming to support economic regeneration or accommodate economic growth by unlocking or enabling the development of brownfield or greenfield for employment or residential uses. These projects would include direct investments in property development, investments in land reclamation or remediation, as well as the provisioning of site services (including access roads) to enable their onward development.
Enhancing regional and subregional connectivity | Projects aiming to improve connectivity between areas by creating new routes between areas, reducing congestion, or otherwise reducing journey times. These include direct investments in new or improved road or rail links, as well as enhancements to other forms of public transport. Active travel projects, such as new or improved cyclepaths and walkways should be categorised as improving quality of life.
Employment and education | Projects that aim to improve the level of skills attainment by increasing access to education, training and career opportunities. These include support for businesses to create jobs, new or improved education, community, and leisure facilities to be used for learning and developing skills.
Standard outputs
PF-USER_STANDARD-OUTPUTS-START
Intervention theme | Output | Unit of measurement | Baseline output | Total cumulative outputs to date |  | Financial year 2024 to 2025 |  |  |  |  | Financial year 2025 to 2026 |  |  |  |  | Financial year 2026 to 2027 |  |  |  |  | April 2027 and after | Grand total | Variance % (Between MR and Baseline)
|  |  |  | (Up to and including Mar 2024) | Total | (Apr to Jun) | (Jul to Sep) | (Oct to Dec) | (Jan to Mar) | Total | (Apr to Jun) | (Jul to Sep) | (Oct to Dec) | (Jan to Mar) | Total | (Apr to Jun) | (Jul to Sep) | (Oct to Dec) | (Jan to Mar) | Total | Total
|  |  |  | Actual |  | Actual | Actual | Forecast | Forecast |  | Forecast | Forecast | Forecast | Forecast |  | Forecast | Forecast | Forecast | Forecast
Enhancing subregional and regional connectivity | Total length of new pedestrian paths | km | 4.39 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 1 | 44 | 902.3%
Enhancing subregional and regional connectivity | Total length of new cycle ways | km | 4.39 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 45 | 925.1%
Enhancing subregional and regional connectivity | Total length of improved cycle ways | km | 5.05 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 3 | 46 | 810.9%
Enhancing subregional and regional connectivity | Total length of resurfaced/improved road | km | 2.38 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 4 | 47 | 1875%
Enhancing subregional and regional connectivity | Total length of newly built roads | km | 0.13 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 5 | 48 | 36823%
Enhancing subregional and regional connectivity | Number of alternative fuel charging/re-fuelling points | n of | 18 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 6 | 49 | 172.2%
Unlocking and enabling industrial commercial and residential development | Amount of rehabilitated land | sqm | 32500 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 7 | 50 | -99.85%
Unlocking and enabling industrial commercial and residential development | Number of dilapidated buildings improved OR Number of derelict buildings refurbished | n of | 1 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 8 | 51 | 5000%
Unlocking and enabling industrial commercial and residential development | Amount of floor space repurposed (residential, commercial, retail) | sqm | 2900 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 9 | 52 | -98.21%
Strengthening the visitor and local service economy | Amount of public realm improved | sqm | 3504 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 0 | 43 | -98.77%
Strengthening the visitor and local service economy | Number of public amenities/facilities created | n of | 2 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 1 | 44 | 2100%
Strengthening the visitor and local service economy | Number of public amenities/facilities improved | n of | 1 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 45 | 4400%
Strengthening the visitor and local service economy | Number of new community/sports centres | n of | 1 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 3 | 46 | 4500%
Strengthening the visitor and local service economy | Number of heritage buildings renovated/restored OR Number of buildings renovated/restored | n of | 1 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 4 | 47 | 4600%
Strengthening the visitor and local service economy | Number of improved cultural facilities | n of | 2 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 5 | 48 | 2300%
Strengthening the visitor and local service economy | Number of improved community/sports centres | n of | 1 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 6 | 49 | 4800%
Improving the quality of life of residents | Number of trees planted OR Number of new trees planted | n of | 103 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 7 | 50 | -51.46%
Improving the quality of life of residents | Amount of existing parks/greenspace/outdoor improved | sqm | 0 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 8 | 51 | 0%
Improving the quality of life of residents | Amount of new parks/greenspace/outdoor space | sqm | 3048 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 9 | 52 | -98.29%
Employment and education | n of full-time equivalent (FTE) permanent jobs created directly through the projects | n of | 835 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 0 | 43 | -94.85%
Employment and education | n of full-time equivalent (FTE) permanent jobs safeguarded directly through the projects | n of | 10003 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 1 | 44 | -99.56%
Employment and education | n of full-time equivalent (FTE) permanent jobs facilitated directly through the projects | n of | 1304 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 45 | -96.55%
Employment and education | n of temporary FT jobs supported during project implementation | n of | 381 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 3 | 46 | -87.93%
Employment and education | Amount of new educational space created | sqm | 6800 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 4 | 47 | -99.31%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
[23 empty] | PF-USER_STANDARD-OUTPUTS-END | n of
Bespoke outputs
PF-USER_BESPOKE-OUTPUTS-START
Intervention theme | Output | Unit of measurement | Baseline output | Total cumulative outputs to date |  | Financial year 2024 to 2025 |  |  |  |  | Financial year 2025 to 2026 |  |  |  |  | Financial year 2026 to 2027 |  |  |  |  | April 2027 and after | Grand total | Variance % (Between MR and Baseline)
|  |  |  | (Up to and including Mar 2024) | Total | (Apr to Jun) | (Jul to Sep) | (Oct to Dec) | (Jan to Mar) | Total | (Apr to Jun) | (Jul to Sep) | (Oct to Dec) | (Jan to Mar) | Total | (Apr to Jun) | (Jul to Sep) | (Oct to Dec) | (Jan to Mar) | Total | Total
|  |  |  | Actual |  | Actual | Actual | Forecast | Forecast |  | Forecast | Forecast | Forecast | Forecast |  | Forecast | Forecast | Forecast | Forecast
Bespoke | Amount of new office space (m2) | sqm | 370 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 1 | 44 | -88.11%
Bespoke | Amount of capacity of new or improved training or education facilities (people) | n of | 557 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 45 | -91.92%
Bespoke | Amount of public realm created (sqm) | sqm | 7279 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 3 | 46 | -99.37%
Bespoke | % increase in participation | % | 10 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 4 | 47 | 370%
Bespoke | % increase in membership | % | 10 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 5 | 48 | 380%
Bespoke | % increase in Health Pathway referrals | % | 40 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 6 | 49 | 22.5%
Bespoke | Number of residential units | n of | 98 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 7 | 50 | -48.98%
Bespoke | Amount of new healthcare facilities sqm | sqm | 6800 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 8 | 51 | -99.25%
Bespoke | Number of new parking spaces | n of | 319 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 9 | 52 | -83.7%
Bespoke | Additional Learners (FE) | n of | 1000 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 0 | 43 | -95.7%
Bespoke | Additional Learners (HE) | n of | 1000 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 1 | 44 | -95.6%
Bespoke | Additional Learners (CPD) | n of | 1000 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 45 | -95.5%
Bespoke | Learners moving into Healthcare from other sectors | n of | 950 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 3 | 46 | -95.16%
Bespoke | Local employment (NHS workers living within 10 mile radious) | n of | 500 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 4 | 47 | -90.6%
Bespoke | Increase in the amount of diversity of commercial floorspace (sqm) | sqm | 750 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 5 | 48 | -93.6%
Bespoke | Increase in existing visits (%) | % | 20 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 6 | 49 | 145%
Bespoke | Increase in dwell time (%) | % | 7 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 7 | 50 | 614.3%
Bespoke | Increase in number of trading units | n of | 20 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 8 | 51 | 155%
Bespoke | Number of new awnings & food hall | n of | 1 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 9 | 52 | 5100%
Bespoke | Increase in amount of shared innovation facilities (%) | % | 15 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 0 | 43 | 186.7%
Bespoke | Increase in amount of new specialist technology equipment (%) | % | 20 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 1 | 44 | 120%
Bespoke | Increase in uptake of digital/technical apprenticeships (%) | % | 10 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 45 | 350%
Bespoke | Increase in the share of young people & adults who have the relevant skills for employment & entrepreneurship (%) | % | 10 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 3 | 46 | 360%
Bespoke | Increase in new business start ups (%) | % | 20 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 4 | 47 | 135%
Bespoke | Increase in business scale ups (%) | % | 20 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 5 | 48 | 140%
Bespoke | Increase in no of visitors to arts, culture & heritage events | n of | 20 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 6 | 49 | 145%
Bespoke | Rehabilitated land m2 | sqm | 32374 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 7 | 50 | -99.85%
Bespoke | Improved parking spaces | n of | 406 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 8 | 51 | -87.44%
Bespoke | Sites cleared | n of | 6 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 9 | 52 | 766.7%
Bespoke | Additional enterprises with broadband access | n of | 15 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 0 | 43 | 186.7%
Bespoke | Non domestic buildings with green retrofit | n of | 1 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 1 | 44 | 4300%
Bespoke | Office Space renovated/improved | sqm | 5574 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 45 | -99.19%
Bespoke | Potential entrepreneurs assisted | n of | 20 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 3 | 46 | 130%
Bespoke | Closer collaboration with employers | n of | 10 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 4 | 47 | 370%
Bespoke | Increase in capacity and accessibility to new/improved facilities | % | 15 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 5 | 48 | 220%
Bespoke | m2 of Heritage buildings renovated/restored | sqm | 1962 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 6 | 49 | -97.5%
Bespoke | Improved perception of place (%) visitors, businesses, residents | % | 20 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 7 | 50 | 150%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
PF-USER_BESPOKE-OUTPUTS-END

## Outcomes
Outcomes
What have you delivered, and what is forecast to be delivered?
Tell us about the outputs you are delivering and the outcomes these are achieving, or expected to achieve. Provide this at portfolio level by intervention theme. Investment themes have been developed to help MHCLG evaluate how our funds are helping to achieve Levelling Up. Investment themes are designed to organise outputs and outcomes by the objective of the project rather than the nature of the activities being undertaken. This is because similar projects can have different objectives and different activities can achieve the same result. For example, road improvements can facilitate development by linking a site to the road network or strengthen the service economy by making it easier to access a visitor attraction. When selecting an investment theme, think about the main long term objective of delivering the output or outcome.
Description of investment themes
Intervention theme | Description
Improving quality of life for residents | Projects where the principal aim is to improve the quality of life of residents by improving the quality of local public services and associated infrastructure. Projects funded under this heading are diverse: including improvements to educational, health, leisure and community facilities, environmental amenities (for example, parks), investments in new or improved social housing stock, and provisioning of cycling and walking infrastructure.
Strengthening the local service economy | Projects aiming to support economic regeneration via stimulating greater levels of consumer spending in local economies. These include investments in culture or heritage assets that serve as visitor attractions, investments in the public realm (for example, town centre improvement projects or enhancements to other infrastructure to improve the visitor experience), and provisioning of new or improved retail floorspace.
Unlocking commercial, industrial and residential development | Projects aiming to support economic regeneration or accommodate economic growth by unlocking or enabling the development of brownfield or greenfield for employment or residential uses. These projects would include direct investments in property development, investments in land reclamation or remediation, as well as the provisioning of site services (including access roads) to enable their onward development.
Enhancing regional and subregional connectivity | Projects aiming to improve connectivity between areas by creating new routes between areas, reducing congestion, or otherwise reducing journey times. These include direct investments in new or improved road or rail links, as well as enhancements to other forms of public transport. Active travel projects, such as new or improved cyclepaths and walkways should be categorised as improving quality of life.
Employment and education | Projects that aim to improve the level of skills attainment by increasing access to education, training and career opportunities. These include support for businesses to create jobs, new or improved education, community, and leisure facilities to be used for learning and developing skills.
Standard outcomes
PF-USER_STANDARD-OUTCOMES-START
Intervention theme | Outcome | Unit of measurement | Baseline outcome | Total cumulative outcomes to date |  | Financial year 2024 to 2025 |  |  |  |  | Financial year 2025 to 2026 |  |  |  |  | Financial year 2026 to 2027 |  |  |  |  | April 2027 and after | Grand total | Variance % (Between MR and Baseline)
|  |  |  | (Up to and including Mar 2024) | Total | (Apr to Jun) | (Jul to Sep) | (Oct to Dec) | (Jan to Mar) | Total | (Apr to Jun) | (Jul to Sep) | (Oct to Dec) | (Jan to Mar) | Total | (Apr to Jun) | (Jul to Sep) | (Oct to Dec) | (Jan to Mar) | Total | Total
|  |  |  | Actual |  | Actual | Actual | Forecast | Forecast |  | Forecast | Forecast | Forecast | Forecast |  | Forecast | Forecast | Forecast | Forecast
Enhancing subregional and regional connectivity | Footfall | n of | 1220007 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 1 | 44 | -100%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
PF-USER_STANDARD-OUTCOMES-END
Bespoke outcomes
PF-USER_BESPOKE-OUTCOMES-START
Intervention theme | Outcome | Unit of measurement | Baseline outcome | Total cumulative outcomes to date |  | Financial year 2024 to 2025 |  |  |  |  | Financial year 2025 to 2026 |  |  |  |  | Financial year 2026 to 2027 |  |  |  |  | April 2027 and after | Grand total | Variance % (Between MR and Baseline)
|  |  |  | (Up to and including Mar 2024) | Total | (Apr to Jun) | (Jul to Sep) | (Oct to Dec) | (Jan to Mar) | Total | (Apr to Jun) | (Jul to Sep) | (Oct to Dec) | (Jan to Mar) | Total | (Apr to Jun) | (Jul to Sep) | (Oct to Dec) | (Jan to Mar) | Total | Total
|  |  |  | Actual |  | Actual | Actual | Forecast | Forecast |  | Forecast | Forecast | Forecast | Forecast |  | Forecast | Forecast | Forecast | Forecast
Bespoke | Travel times in corridors of interest | % | 10 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 1 | 44 | 340%
Bespoke | Number of enterprises receiving non financial support | n of | 25 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 45 | 80%
Bespoke | No of births of new enterprises | n of | 33 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 3 | 46 | 39.39%
Bespoke | Average occupany rates work spaces (5) | n of | 515 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 4 | 47 | -90.87%
Bespoke | (%) of adults satisfied with their area | % | 30 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 5 | 48 | 60%
Bespoke | (%) of visitors likely to recommend the town | % | 10 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 6 | 49 | 390%
Bespoke | No of people using an improved/new public facility (%) | n of | 20 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 7 | 50 | 150%
Bespoke | (%) of customers or visitors who report a positive experience | % | 5 | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 2 | 3 | 4 | 5 | 14 | 8 | 51 | 920%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
PF-USER_BESPOKE-OUTCOMES-END

## Finances
Finances
Portfolio-level finances
The following questions refer to the current financial year that you are reporting against.
PF-USER_CURRENT-UNDERSPEND-START
Current underspend
What is the current underspend for this financial year?
Enter numbers only
250
PF-USER_CURRENT-UNDERSPEND-END
Forecast and actual spend - Capital
PF-USER_FORECAST-AND-ACTUAL-SPEND-CAPITAL-START
Type of spend | Total cumulative actuals to date |  | Financial year 2024 to 2025 |  |  |  |  | Financial year 2025 to 2026 |  |  |  |  | Financial year 2026 to 2027 |  |  |  |  | Grand total
| (Up to and including Mar 2024) | Total | (Apr to Jun) | (Jul to Sep) | (Oct to Dec) | (Jan to Mar) | Total | (Apr to Jun) | (Jul to Sep) | (Oct to Dec) | (Jan to Mar) | Total | (Apr to Jun) | (Jul to Sep) | (Oct to Dec) | (Jan to Mar) | Total
| Actual |  | Actual | Actual | Forecast | Forecast |  | Forecast | Forecast | Forecast | Forecast |  | Forecast | Forecast | Forecast | Forecast
How much of your forecast is contractually committed (this includes actual expenditure)? | 1 | 1 | fesf | 3 | 4 | 5 | 12 | 6 | 7 | 8 | 9 | 30 | 1 | 2 | 3 | 4 | 10 | 53
How much of your forecast is not contractually committed? | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 6 | 7 | 8 | 9 | 30 | 1 | 2 | 3 | 4 | 10 | 55
Freedom and flexibilities spend | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 6 | 7 | 8 | 9 | 30 | 1 | 2 | 3 | 4 | 10 | 55
Total MHCLG spend (inc. F&F) | 3 | 3 | 4 | 9 | 12 | 15 | 40 | 18 | 21 | 24 | 27 | 90 | 3 | 6 | 9 | 12 | 30 | 163
Secured match funding spend (this includes actual match funding) | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 6 | 7 | 8 | 9 | 30 | 1 | 2 | 3 | 4 | 10 | 55
Unsecured match funding | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 6 | 7 | 8 | 9 | 30 | 1 | 2 | 3 | 4 | 10 | 55
Total match | 2 | 2 | 4 | 6 | 8 | 10 | 28 | 12 | 14 | 16 | 18 | 60 | 2 | 4 | 6 | 8 | 20 | 110
Total | 5 | 5 | 8 | 15 | 20 | 25 | 68 | 30 | 35 | 40 | 45 | 150 | 5 | 10 | 15 | 20 | 50 | 273
PF-USER_FORECAST-AND-ACTUAL-SPEND-CAPITAL-END
Forecast and actual spend - Revenue
PF-USER_FORECAST-AND-ACTUAL-SPEND-REVENUE-START
Type of spend | Total cumulative actuals to date |  | Financial year 2024 to 2025 |  |  |  |  | Financial year 2025 to 2026 |  |  |  |  | Financial year 2026 to 2027 |  |  |  |  | Grand total
| (Up to and including Mar 2024) | Total | (Apr to Jun) | (Jul to Sep) | (Oct to Dec) | (Jan to Mar) | Total | (Apr to Jun) | (Jul to Sep) | (Oct to Dec) | (Jan to Mar) | Total | (Apr to Jun) | (Jul to Sep) | (Oct to Dec) | (Jan to Mar) | Total
| Actual |  | Actual | Actual | Forecast | Forecast |  | Forecast | Forecast | Forecast | Forecast |  | Forecast | Forecast | Forecast | Forecast
How much of your forecast is contractually committed (this includes actual expenditure)? | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 6 | 7 | 8 | 9 | 30 | 1 | 2 | 3 | 4 | 10 | 55
How much of your forecast is not contractually committed? | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 6 | 7 | 8 | 9 | 30 | 1 | 2 | 3 | 4 | 10 | 55
Freedom and flexibilities spend | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 6 | ine | 8 | 9 | 23 | 1 | 2 | 3 | 4 | 10 | 48
Total MHCLG spend (inc. F&F) | 3 | 3 | 6 | 9 | 12 | 15 | 42 | 18 | 14 | 24 | 27 | 83 | 3 | 6 | 9 | 12 | 30 | 158
Secured match funding spend (this includes actual match funding) | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 6 | 7 | 8 | 9 | 30 | 1 | 2 | 3 | 4 | 10 | 55
Unsecured match funding | 1 | 1 | 2 | 3 | 4 | 5 | 14 | 6 | 7 | 8 | 9 | 30 | 1 | 2 | 3 | 4 | 10 | 55
Total match | 2 | 2 | 4 | 6 | 8 | 10 | 28 | 12 | 14 | 16 | 18 | 60 | 2 | 4 | 6 | 8 | 20 | 110
Total | 5 | 5 | 10 | 15 | 20 | 25 | 70 | 30 | 28 | 40 | 45 | 143 | 5 | 10 | 15 | 20 | 50 | 268
PF-USER_FORECAST-AND-ACTUAL-SPEND-REVENUE-END
PF-USER_UNCOMMITTED-FUNDING-PLAN-START
Uncommitted funding plan
What is your plan for using any uncommitted funding?
Please set out how uncommitted funding will be used, indicating when funds will become committed. This should cover your underspend as detailed above and remaining uncommitted allocation. Please write "N/A" if all of your funding is committed.
I don't have a plan. I think I'll just wing-it.
500 words suggested | [5 empty] | PF-USER_UNCOMMITTED-FUNDING-PLAN-END
PF-USER_SUMMARY-OF-CHANGES-BELOW-CHANGE-REQUEST-THRESHOLD-START
Summary of changes below change request threshold
What changes have you made, or plan to make, that are below the change request threshold?
The threshold is £5m or more moved between projects or intervention themes. Changes below the threshold could include: reallocating funding between projects; making an adjustment to a project and delivering different outputs/outcomes; scrapping a project; delivering a new project; or moving funding between geographical areas within the local authority.
No changes made yet.
500 words suggested | [5 empty] | PF-USER_SUMMARY-OF-CHANGES-BELOW-CHANGE-REQUEST-THRESHOLD-END
Project finance changes
Only include changes where the amount moved falls below the change request threshold.
PF-USER_PROJECT-FINANCE-CHANGES-START
Change number | Project funding moved from |  | Intervention theme moved from |  | Project funding moved to |  | Intervention theme moved to |  | Amount moved | What changes have you made / or are planning to make? (100 words max) |  | Reason for change (100 words max) | [6 empty] | Actual, forecast or cancelled | Reporting period change takes place
1 | PF-BOL-008: Streets for All - Farnworth |  | Enhancing subregional and regional connectivity |  | PF-BOL-008: Streets for All - Farnworth |  | Enhancing subregional and regional connectivity |  | 1234567 | Moved x to y |  | Because I needed test data. | [6 empty] | Actual | Q1 2024/25: Apr 2024 - Jun 2024
| Please select an option |  | Please select an option |  | Please select an option |  | Please select an option | [11 empty] | Please select an option | Please select an option
| Please select an option |  | Please select an option |  | Please select an option |  | Please select an option | [11 empty] | Please select an option | Please select an option
| Please select an option |  | Please select an option |  | Please select an option |  | Please select an option | [11 empty] | Please select an option | Please select an option
| Please select an option |  | Please select an option |  | Please select an option |  | Please select an option | [11 empty] | Please select an option | Please select an option
| Please select an option |  | Please select an option |  | Please select an option |  | Please select an option | [11 empty] | Please select an option | Please select an option
| Please select an option |  | Please select an option |  | Please select an option |  | Please select an option | [11 empty] | Please select an option | Please select an option
| Please select an option |  | Please select an option |  | Please select an option |  | Please select an option | [11 empty] | Please select an option | Please select an option
| Please select an option |  | Please select an option |  | Please select an option |  | Please select an option | [11 empty] | Please select an option | Please select an option
| Please select an option |  | Please select an option |  | Please select an option |  | Please select an option | [11 empty] | Please select an option | Please select an option
| Please select an option |  | Please select an option |  | Please select an option |  | Please select an option | [11 empty] | Please select an option | Please select an option
| Please select an option |  | Please select an option |  | Please select an option |  | Please select an option | [11 empty] | Please select an option | Please select an option
| Please select an option |  | Please select an option |  | Please select an option |  | Please select an option | [11 empty] | Please select an option | Please select an option
| Please select an option |  | Please select an option |  | Please select an option |  | Please select an option | [11 empty] | Please select an option | Please select an option
| Please select an option |  | Please select an option |  | Please select an option |  | Please select an option | [11 empty] | Please select an option | Please select an option
| Please select an option |  | Please select an option |  | Please select an option |  | Please select an option | [11 empty] | Please select an option | Please select an option
| Please select an option |  | Please select an option |  | Please select an option |  | Please select an option | [11 empty] | Please select an option | Please select an option
| Please select an option |  | Please select an option |  | Please select an option |  | Please select an option | [11 empty] | Please select an option | Please select an option
PF-USER_PROJECT-FINANCE-CHANGES-END
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The order of questions in this sheet feels off. In Mural we ask for the committed and forecast spend first, then follow with uncommitted, underspend, credible plan and changes. Reply: Does it matter to the user what order they fill these out in? Or do some topics / data points logically follow on from others?

## Risks
Risks
What are the main risks across your portfolio? Please enter five.
If you have resolved a risk since your last submission, log it here as closed and tell us how well your mitigations worked. We use this information to see how problems get solved, so we can share that knowledge with others.
PF-USER_RISKS-START
Risk name | Category | Description | Pre-mitigated likelihood score | Pre-mitigated impact score | Pre-mitigated total risk score | Mitigations | Post-mitigated likelihood score | Post-mitigated impact score | Post-mitigated total risk score
| Select risk categories applicable to the portfolio. | Explain what might go wrong and why, and what the outcome would be if it did. (100 words maximum) | What is the probability of this happening, based on mitigations already in place? | To what extent would this affect delivery, based on mitigations already in place? | We calculate this by multiplying the likelihood score with the impact score. | Explain the mitigations you had, have, or plan to have in place to manage the risk. (100 words maximum) | What level of confidence do you have that the risk has now been mitigated? | To what extent did the mitigations ensure that delivery was not affected? | We calculate this by multiplying the likelihood score with the impact score.
1 | Arm’s length body risks | Everything - then disaster! | 5 - Very High | 1 - Very Low | 5 | Crossed fingers | 4 - High | 1 - Very Low | 4
2 | Commercial or procurement risks | Everything - then disaster! | 4 - High | 2 - Low | 8 | Crossed fingers | 2 - Low | 3 - Medium | 6
3 | Delivery Partner | Everything - then disaster! | 3 - Medium | 3 - Medium | 9 | Crossed fingers | 5 - Very High | 5 - Very High | 25
4 | Financial flexibility | Everything - then disaster! | 2 - Low | 4 - High | 8 | Crossed fingers | 3 - Medium | 2 - Low | 6
5 | Financial risks | Everything - then disaster! | 1 - Very Low | 5 - Very High | 5 | Crossed fingers | 1 - Very Low | 4 - High | 4
PF-USER_RISKS-END

## Sign off
Sign off
Please ensure this document is signed by the Section 151 Officer or Chief Finance Officer. No other signatories will be accepted.
Section 151 Officer or Chief Finance Officer
I confirm that: • the information in this document is accurate • all significant issues affecting deliverability of the project have been disclosed • the Board has seen this document before submission
PF-USER_SIGNATORY-NAME-START
Signatory name
Me
PF-USER_SIGNATORY-NAME-END
PF-USER_SIGNATORY-ROLE-START
Signatory role
VIP
PF-USER_SIGNATORY-ROLE-END
PF-USER_SIGNATURE-IMAGE-START
Signature image
This must be an image
x
PF-USER_SIGNATURE-IMAGE-END
PF-USER_SIGNATURE-DATE-START
Signature date
Enter following this format: dd/mm/yyyy
2024-10-24
PF-USER_SIGNATURE-DATE-END
Council Leader | [8 empty] | Enumeration Values
Name | [8 empty] | <Select>
Role | [8 empty] | Yes
Confirm information provided is accurate | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No
Date (dd/mm/yyyy)

## Dropdown Values
PF-CONTROL_GLOBAL-DROPDOWN-PLACEHOLDER-START
Global dropdown placeholder
Please select an option
PF-CONTROL_GLOBAL-DROPDOWN-PLACEHOLDER-END
PF-CONTROL_REPORTING-PERIOD-START
Reporting period
Please select an option
Q4 2023/24: Jan 2024 - Mar 2024
Q1 2024/25: Apr 2024 - Jun 2024
Q2 2024/25: Jul 2024 - Sep 2024
Q3 2024/25: Oct 2024 - Dec 2024
Q4 2024/25: Jan 2025 - Mar 2025
Q1 2025/26: Apr 2025 - Jun 2025
Q2 2025/26: Jul 2025 - Sep 2025
Q3 2025/26: Oct 2025 - Dec 2025
Q4 2025/26: Jan 2026 - Mar 2026
Q1 2026/27: Apr 2026 - Jun 2026
Q2 2026/27: Jul 2026 - Sep 2026
Q3 2026/27: Oct 2026 - Dec 2026
Q4 2026/27: Jan 2027 - Mar 2027
PF-CONTROL_REPORTING-PERIOD-END
PF-CONTROL_ORGANISATION-NAME-START
Organisation name
Please select an option
Bolton Council
Calderdale Council
City of Wolverhampton Council
Lewes District Council
Nuneaton & Bedworth Borough Council
Rotherham Metropolitan Borough Council
Sheffield City Council
Stockton-on-Tees Borough Council
Thanet District Council
Wirral Council
PF-CONTROL_ORGANISATION-NAME-END
PF-CONTROL_PROJECT-STATUS-START
Project status
Please select an option
Not started
In progress
On hold
Project cancelled
Project complete
PF-CONTROL_PROJECT-STATUS-END
PF-CONTROL_RAG-RATING-START
Progress RAG rating
Please select an option
Green
Amber/Green
Amber
Amber/Red
Red
PF-CONTROL_RAG-RATING-END
PF-CONTROL_STANDARD-OUTPUTS-START
Standard output | UoM | Intervention theme
Please select an option | #N/A
Amount of existing hospitality space improved | sqm | Strengthening the visitor and local service economy
Amount of existing parks/greenspace/outdoor improved | sqm | Improving the quality of life of residents
Amount of existing retail space improved | sqm | Strengthening the visitor and local service economy
Amount of floor space repurposed (residential, commercial, retail) | sqm | Unlocking and enabling industrial commercial and residential development
Amount of land made wheelchair accessible/step free | sqm | Enhancing sub-regional and regional connectivity
Amount of new educational space created | sqm | Employment and education
Amount of new hospitality space created | sqm | Strengthening the visitor and local service economy
Amount of new parks/greenspace/outdoor space | sqm | Improving the quality of life of residents
Amount of new retail space created | sqm | Strengthening the visitor and local service economy
Amount of public realm improved | sqm | Strengthening the visitor and local service economy
Amount of rehabilitated land | sqm | Unlocking and enabling industrial commercial and residential development
n of full-time equivalent (FTE) permanent jobs created directly through the projects | n of | Employment and education
n of full-time equivalent (FTE) permanent jobs facilitated directly through the projects | n of | Employment and education
n of full-time equivalent (FTE) permanent jobs safeguarded directly through the projects | n of | Employment and education
n of temporary FT jobs supported during project implementation | n of | Employment and education
Number of alternative fuel charging/re-fuelling points | n of | Enhancing sub-regional and regional connectivity
Number of dilapidated buildings improved OR Number of derelict buildings refurbished | n of | Unlocking and enabling industrial commercial and residential development
Number of heritage buildings renovated/restored OR Number of buildings renovated/restored | n of | Strengthening the visitor and local service economy
Number of improved community/sports centres | n of | Strengthening the visitor and local service economy
Number of improved cultural facilities | n of | Strengthening the visitor and local service economy
Number of local events or activities supported | n of | Strengthening the visitor and local service economy
Number of neighbourhood improvements undertaken | n of | Strengthening the visitor and local service economy
Number of new community/sports centres | n of | Strengthening the visitor and local service economy
Number of new cultural facilities | n of | Strengthening the visitor and local service economy
Number of properties better protected from flooding and coastal erosion | n of | Improving the quality of life of residents
Number of public amenities/facilities created | n of | Strengthening the visitor and local service economy
Number of public amenities/facilities improved | n of | Strengthening the visitor and local service economy
Number of trees planted OR Number of new trees planted | n of | Improving the quality of life of residents
Total length of improved cycle ways | km | Enhancing sub-regional and regional connectivity
Total length of new cycle ways | km | Enhancing sub-regional and regional connectivity
Total length of new pedestrian paths | km | Enhancing sub-regional and regional connectivity
Total length of newly built roads | km | Enhancing sub-regional and regional connectivity
Total length of pedestrian paths improved | km | Enhancing sub-regional and regional connectivity
Total length of resurfaced/improved road | km | Enhancing sub-regional and regional connectivity
PF-CONTROL_STANDARD-OUTPUTS-END
PF-CONTROL_STANDARD-OUTCOMES-START
Standard outcome | UoM | Intervention theme
Please select an option | #N/A | #N/A
Audience numbers for cultural events | n of | Strengthening the visitor and local service economy
Change in number of properties better protected from flooding and coastal erosion | % | Improving the quality of life of residents
Change in perceived/experienced accessibility | % | Enhancing sub-regional and regional connectivity
Cycle flow | n of | Enhancing sub-regional and regional connectivity
Footfall | n of | Enhancing sub-regional and regional connectivity
Number of anti-social behaviour crimes recorded | n of | Strengthening the visitor and local service economy
Number of anti-social behaviour crimes recorded | n of | Improving the quality of life of residents
Number of crimes reported | n of | Strengthening the visitor and local service economy
Number of crimes reported | n of | Improving the quality of life of residents
Number of cultural events | n of | Strengthening the visitor and local service economy
Number of day visitors | n of | Strengthening the visitor and local service economy
Number of major commercial planning applications granted | n of | Unlocking and enabling industrial commercial and residential development
Number of minor commercial planning applications granted | n of | Unlocking and enabling industrial commercial and residential development
Number of people using a new/improved public facility | n of | Strengthening the visitor and local service economy
Number of visitors to cultural venues | n of | Strengthening the visitor and local service economy
Pedestrian flow | n of | Enhancing sub-regional and regional connectivity
Percentage of adults who are satisfied with their local area as a place to live | % | Unlocking and enabling industrial commercial and residential development
Percentage of residents who report feeling safe in their local area | % | Strengthening the visitor and local service economy
Percentage of residents who report feeling safe in their local area | % | Improving the quality of life of residents
Public transport reliability | % | Enhancing sub-regional and regional connectivity
Total consumer spending at cultural venues | £ | Strengthening the visitor and local service economy
Vacancy rate of commercial units | % | Strengthening the visitor and local service economy
Vehicle flow | n of | Enhancing sub-regional and regional connectivity
PF-CONTROL_STANDARD-OUTCOMES-END
PF-CONTROL_UNIT-OF-MEASUREMENT-START
Unit of measurement
Please select an option
km
n of
sqm
%
£
PF-CONTROL_UNIT-OF-MEASUREMENT-END
PF-CONTROL_INTERVENTION-THEME-START
Intervention theme
Please select an option
Employment and education
Enhancing subregional and regional connectivity
Improving the quality of life of residents
Strengthening the visitor and local service economy
Unlocking and enabling industrial commercial and residential development
PF-CONTROL_INTERVENTION-THEME-END
PF-CONTROL_INTERVENTION-THEME-BESPOKE-START
Bespoke intervention theme
Please select an option
Bespoke
PF-CONTROL_INTERVENTION-THEME-BESPOKE-END
PF-CONTROL_CREDIBLE-PLAN-START
Credible plan yes or no
Please select an option
Yes
No
PF-CONTROL_CREDIBLE-PLAN-END
PF-CONTROL_ACTUAL-FORECAST-CANCELLED-START
Actual, forecast or cancelled
Please select an option
Actual
Forecast
Cancelled
PF-CONTROL_ACTUAL-FORECAST-CANCELLED-END
PF-CONTROL_RISK-CATEGORY-START
Risk category
Please select an option
Arm’s length body risks
Commercial or procurement risks
Delivery Partner
Financial flexibility
Financial risks
Governance risks
Legal, regulatory or compliance risks
Local government risks
Operational process or control risks
People risks
Planning Permission / other consents
Political sensitivity
Procurement / contracting
Programme or project delivery risks
Reputational Risk
Resilience risks
Resource & Expertise
Security risks
Slippage
Strategy risks
Subsidy Control
System or IT infrastructure risks
Other
PF-CONTROL_RISK-CATEGORY-END
PF-CONTROL_RISK-SCORE-START
Risk score
Please select an option
5 - Very High
4 - High
3 - Medium
2 - Low
1 - Very Low
PF-CONTROL_RISK-SCORE-END

## Project Details (hidden)
PF-CONTROL_PROJECT-DETAILS-START
Local Authority | Reference | Project name | Status | Full name
Bolton Council | PF-BOL-001 | Wellsprings Innovation Hub | Active | PF-BOL-001: Wellsprings Innovation Hub
Bolton Council | PF-BOL-002 | Bolton Market Upgrades | Active | PF-BOL-002: Bolton Market Upgrades
Bolton Council | PF-BOL-003 | Bolton Library & Museum Upgrade | Active | PF-BOL-003: Bolton Library & Museum Upgrade
Bolton Council | PF-BOL-004 | Public Realm Improvements | Active | PF-BOL-004: Public Realm Improvements
Bolton Council | PF-BOL-005 | Accelerated Funding £1 million Public Realm Improvements | Active | PF-BOL-005: Accelerated Funding £1 million Public Realm Improvements
Bolton Council | PF-BOL-006 | Farnworth Market Precinct | Active | PF-BOL-006: Farnworth Market Precinct
Bolton Council | PF-BOL-007 | Farnworth Leisure Centre Expansion | Active | PF-BOL-007: Farnworth Leisure Centre Expansion
Bolton Council | PF-BOL-008 | Streets for All - Farnworth | Active | PF-BOL-008: Streets for All - Farnworth
Bolton Council | PF-BOL-009 | Bolton College of Medical Science | Active | PF-BOL-009: Bolton College of Medical Science
Calderdale Council | PF-CAL-001 | Todmorden 01 Public Places in the Heart of Todmorden | Active | PF-CAL-001: Todmorden 01 Public Places in the Heart of Todmorden
Calderdale Council | PF-CAL-002 | Todmorden 02 Todmorden Town Hall | Active | PF-CAL-002: Todmorden 02 Todmorden Town Hall
Calderdale Council | PF-CAL-003 | Todmorden 03 Centre Vale & Fielden Hall | Active | PF-CAL-003: Todmorden 03 Centre Vale & Fielden Hall
Calderdale Council | PF-CAL-004 | Todmorden 04 Hippodrome Theatre | Active | PF-CAL-004: Todmorden 04 Hippodrome Theatre
Calderdale Council | PF-CAL-005 | Todmorden 05 Enterprise in the Heart of Todmorden | Active | PF-CAL-005: Todmorden 05 Enterprise in the Heart of Todmorden
Calderdale Council | PF-CAL-006 | Todmorden 06 Active Todmorden | Active | PF-CAL-006: Todmorden 06 Active Todmorden
Calderdale Council | PF-CAL-007 | Todmorden 07 Todmorden Learning Centre & Community Hub | Active | PF-CAL-007: Todmorden 07 Todmorden Learning Centre & Community Hub
Calderdale Council | PF-CAL-008 | Todmorden 08 Riverside Outdoor Activity & Sports Park | Active | PF-CAL-008: Todmorden 08 Riverside Outdoor Activity & Sports Park
Calderdale Council | PF-CAL-009 | Brighouse 01 Industry 4.0 & Skills | Active | PF-CAL-009: Brighouse 01 Industry 4.0 & Skills
Calderdale Council | PF-CAL-010 | Brighouse 02 Market Revitalisation | Active | PF-CAL-010: Brighouse 02 Market Revitalisation
Calderdale Council | PF-CAL-011 | Brighouse 03 Canalside & Thornton Square | Active | PF-CAL-011: Brighouse 03 Canalside & Thornton Square
Calderdale Council | PF-CAL-012 | Brighouse 04 Welcome | Active | PF-CAL-012: Brighouse 04 Welcome
Calderdale Council | PF-CAL-013 | Brighouse 05 Retail and Leisure Offer | Active | PF-CAL-013: Brighouse 05 Retail and Leisure Offer
Calderdale Council | PF-CAL-014 | Elland 01 Community Hub | Active | PF-CAL-014: Elland 01 Community Hub
Calderdale Council | PF-CAL-015 | Elland 02 Southgate Square | Active | PF-CAL-015: Elland 02 Southgate Square
Calderdale Council | PF-CAL-016 | Elland 03 Heart of the High Street | Active | PF-CAL-016: Elland 03 Heart of the High Street
Calderdale Council | PF-CAL-017 | Elland 04 Market Area | Active | PF-CAL-017: Elland 04 Market Area
Calderdale Council | PF-CAL-018 | Elland 05 Shop Front Improvements | Active | PF-CAL-018: Elland 05 Shop Front Improvements
Calderdale Council | PF-CAL-019 | Halifax 01 Alleyways | Active | PF-CAL-019: Halifax 01 Alleyways
Calderdale Council | PF-CAL-020 | Halifax 02 George Square | Active | PF-CAL-020: Halifax 02 George Square
Calderdale Council | PF-CAL-021 | Halifax 03 Palentine Chambers | Active | PF-CAL-021: Halifax 03 Palentine Chambers
Calderdale Council | PF-CAL-022 | Halifax 04 Westgate Phase 2 | Active | PF-CAL-022: Halifax 04 Westgate Phase 2
Calderdale Council | PF-CAL-023 | Halifax 05 Playtrail | Active | PF-CAL-023: Halifax 05 Playtrail
Calderdale Council | PF-CAL-024 | Halifax 06 Victoria Theatre | Active | PF-CAL-024: Halifax 06 Victoria Theatre
Calderdale Council | PF-CAL-025 | Halifax 07 Borough Market | Active | PF-CAL-025: Halifax 07 Borough Market
Calderdale Council | PF-CAL-026 | Halifax 08 Northgate House | Active | PF-CAL-026: Halifax 08 Northgate House
Calderdale Council | PF-CAL-027 | 01 LUF Leisure | Active | PF-CAL-027: 01 LUF Leisure
Calderdale Council | PF-CAL-028 | Todmorden Programme Management | Active | PF-CAL-028: Todmorden Programme Management
Calderdale Council | PF-CAL-029 | Halifax Programme Management | Active | PF-CAL-029: Halifax Programme Management
City of Wolverhampton Council | PF-WOL-001 | Victoria Street Public Realm (FHSF) | Active | PF-WOL-001: Victoria Street Public Realm (FHSF)
City of Wolverhampton Council | PF-WOL-002 | Civic Halls Public Realm (FHSF) | Active | PF-WOL-002: Civic Halls Public Realm (FHSF)
City of Wolverhampton Council | PF-WOL-003 | Bell Street Scheme (FHSF) | Active | PF-WOL-003: Bell Street Scheme (FHSF)
City of Wolverhampton Council | PF-WOL-004 | Brewers Yard | Active | PF-WOL-004: Brewers Yard
City of Wolverhampton Council | PF-WOL-005 | Wolves @ Work | Active | PF-WOL-005: Wolves @ Work
City of Wolverhampton Council | PF-WOL-006 | Events Programme | Active | PF-WOL-006: Events Programme
City of Wolverhampton Council | PF-WOL-007 | Bilston Markets | Active | PF-WOL-007: Bilston Markets
City of Wolverhampton Council | PF-WOL-008 | Wednesfield | Active | PF-WOL-008: Wednesfield
City of Wolverhampton Council | PF-WOL-009 | WM5G | Active | PF-WOL-009: WM5G
City of Wolverhampton Council | PF-WOL-010 | Public Realm (Phase 2) | Active | PF-WOL-010: Public Realm (Phase 2)
City of Wolverhampton Council | PF-WOL-011 | City Learning Quarter | Active | PF-WOL-011: City Learning Quarter
City of Wolverhampton Council | PF-WOL-012 | Arts Park (Phase 1) | Active | PF-WOL-012: Arts Park (Phase 1)
Lewes District Council | PF-LEW-001 | Pedestrian Gateway | Active | PF-LEW-001: Pedestrian Gateway
Lewes District Council | PF-LEW-002 | Newhaven Wayfinding and Public Realm Improvements | Active | PF-LEW-002: Newhaven Wayfinding and Public Realm Improvements
Lewes District Council | PF-LEW-003 | Social Enterprise Incubator | Active | PF-LEW-003: Social Enterprise Incubator
Lewes District Council | PF-LEW-004 | Business Grants Programme | Active | PF-LEW-004: Business Grants Programme
Lewes District Council | PF-LEW-005 | Newhaven Football Club | Active | PF-LEW-005: Newhaven Football Club
Lewes District Council | PF-LEW-006 | Fort Road Recreational Ground | Active | PF-LEW-006: Fort Road Recreational Ground
Lewes District Council | PF-LEW-007 | East Side Recreation Ground | Active | PF-LEW-007: East Side Recreation Ground
Lewes District Council | PF-LEW-008 | Newhaven Fort | Active | PF-LEW-008: Newhaven Fort
Lewes District Council | PF-LEW-009 | Newhaven Ferry Terminal | Active | PF-LEW-009: Newhaven Ferry Terminal
Lewes District Council | PF-LEW-010 | Newhaven Square | Active | PF-LEW-010: Newhaven Square
Lewes District Council | PF-LEW-011 | Fish Landing Stage | Active | PF-LEW-011: Fish Landing Stage
Lewes District Council | PF-LEW-012 | Fish Processing Plan | Active | PF-LEW-012: Fish Processing Plan
Lewes District Council | PF-LEW-013 | Restaurant and Community Destination | Active | PF-LEW-013: Restaurant and Community Destination
Nuneaton & Bedworth Borough Council | PF-NUN-001 | George Eliot Visitor Centre | Active | PF-NUN-001: George Eliot Visitor Centre
Nuneaton & Bedworth Borough Council | PF-NUN-002 | Digital Skills & Innovation Centre | Active | PF-NUN-002: Digital Skills & Innovation Centre
Nuneaton & Bedworth Borough Council | PF-NUN-003 | The Saints | Active | PF-NUN-003: The Saints
Nuneaton & Bedworth Borough Council | PF-NUN-004 | Weddington Road Cycle Scheme | Active | PF-NUN-004: Weddington Road Cycle Scheme
Nuneaton & Bedworth Borough Council | PF-NUN-005 | Visting Nuneaton: Changing Perspectives | Active | PF-NUN-005: Visting Nuneaton: Changing Perspectives
Nuneaton & Bedworth Borough Council | PF-NUN-006 | Wheat Street Junction | Active | PF-NUN-006: Wheat Street Junction
Nuneaton & Bedworth Borough Council | PF-NUN-007 | Corporation Street and Queens Street Junction | Active | PF-NUN-007: Corporation Street and Queens Street Junction
Nuneaton & Bedworth Borough Council | PF-NUN-008 | E-Mobility Hub | Active | PF-NUN-008: E-Mobility Hub
Nuneaton & Bedworth Borough Council | PF-NUN-009 | Parks Revival and Reimagining Nuneaton Museum & Art Gallery | Active | PF-NUN-009: Parks Revival and Reimagining Nuneaton Museum & Art Gallery
Nuneaton & Bedworth Borough Council | PF-NUN-010 | Bedworth Physical Activity Hub | Active | PF-NUN-010: Bedworth Physical Activity Hub
Nuneaton & Bedworth Borough Council | PF-NUN-011 | Grayson Place (Abbey Street) | Active | PF-NUN-011: Grayson Place (Abbey Street)
Nuneaton & Bedworth Borough Council | PF-NUN-012 | Bridge to Living | Active | PF-NUN-012: Bridge to Living
Rotherham Metropolitan Borough Council | PF-ROT-001 | Markets & Library | Active | PF-ROT-001: Markets & Library
Rotherham Metropolitan Borough Council | PF-ROT-002 | Grimm & Co | Active | PF-ROT-002: Grimm & Co
Rotherham Metropolitan Borough Council | PF-ROT-003 | Public Realm - Safe and Smart Streets | Active | PF-ROT-003: Public Realm - Safe and Smart Streets
Rotherham Metropolitan Borough Council | PF-ROT-004 | 3-7 Corporation Street | Active | PF-ROT-004: 3-7 Corporation Street
Rotherham Metropolitan Borough Council | PF-ROT-005 | 30-36 Corporation Street | Active | PF-ROT-005: 30-36 Corporation Street
Rotherham Metropolitan Borough Council | PF-ROT-006 | Essoldo | Active | PF-ROT-006: Essoldo
Rotherham Metropolitan Borough Council | PF-ROT-007 | Parkgate - Eastwood Connectivity | Active | PF-ROT-007: Parkgate - Eastwood Connectivity
Rotherham Metropolitan Borough Council | PF-ROT-008 | Templeborough Business Zone | Active | PF-ROT-008: Templeborough Business Zone
Rotherham Metropolitan Borough Council | PF-ROT-009 | Leisure Economy: Major Attractions | Active | PF-ROT-009: Leisure Economy: Major Attractions
Rotherham Metropolitan Borough Council | PF-ROT-010 | Leisure Economy: Skills | Active | PF-ROT-010: Leisure Economy: Skills
Rotherham Metropolitan Borough Council | PF-ROT-011 | LUF Town Centre: Riverside | Active | PF-ROT-011: LUF Town Centre: Riverside
Rotherham Metropolitan Borough Council | PF-ROT-012 | LUF Town Centre: Leisure & Cultural Quarter | Active | PF-ROT-012: LUF Town Centre: Leisure & Cultural Quarter
Rotherham Metropolitan Borough Council | PF-ROT-013 | Mainline Station | Active | PF-ROT-013: Mainline Station
Sheffield City Council | PF-SHE-001 | Funicular | Active | PF-SHE-001: Funicular
Sheffield City Council | PF-SHE-002 | Little Don Improvement | Active | PF-SHE-002: Little Don Improvement
Sheffield City Council | PF-SHE-003 | Oxley Park & Community Leisure Centre Recreational Infrastructure Development Phase 2 | Active | PF-SHE-003: Oxley Park & Community Leisure Centre Recreational Infrastructure Development Phase 2
Sheffield City Council | PF-SHE-004 | Bus for Stocksbridge | Active | PF-SHE-004: Bus for Stocksbridge
Sheffield City Council | PF-SHE-005 | Cycling and Walking Trails | Active | PF-SHE-005: Cycling and Walking Trails
Sheffield City Council | PF-SHE-006 | Manchester Road Placemaking | Active | PF-SHE-006: Manchester Road Placemaking
Sheffield City Council | PF-SHE-007 | Manchester Road Community Crossover Hub | Active | PF-SHE-007: Manchester Road Community Crossover Hub
Sheffield City Council | PF-SHE-008 | Wellbeing Approach and Hydrotherapy Pool | Active | PF-SHE-008: Wellbeing Approach and Hydrotherapy Pool
Sheffield City Council | PF-SHE-009 | Sports Hub | Active | PF-SHE-009: Sports Hub
Sheffield City Council | PF-SHE-010 | Education and Skills Hub | Active | PF-SHE-010: Education and Skills Hub
Sheffield City Council | PF-SHE-011 | Events Central Building | Active | PF-SHE-011: Events Central Building
Sheffield City Council | PF-SHE-012 | Public Realm and Infrastructure | Active | PF-SHE-012: Public Realm and Infrastructure
Sheffield City Council | PF-SHE-013 | Front Door Scheme | Active | PF-SHE-013: Front Door Scheme
Sheffield City Council | PF-SHE-014 | The Castle | Active | PF-SHE-014: The Castle
Sheffield City Council | PF-SHE-015 | Park Hill Art Space | Active | PF-SHE-015: Park Hill Art Space
Sheffield City Council | PF-SHE-016 | Harmony Works | Active | PF-SHE-016: Harmony Works
Sheffield City Council | PF-SHE-017 | Centre for Child Health Technology | Active | PF-SHE-017: Centre for Child Health Technology
Sheffield City Council | PF-SHE-018 | Connectivity and Movement | Active | PF-SHE-018: Connectivity and Movement
Sheffield City Council | PF-SHE-019 | Adelphi Square | Active | PF-SHE-019: Adelphi Square
Stockton-on-Tees Borough Council | PF-STO-001 | Urban Park | Active | PF-STO-001: Urban Park
Stockton-on-Tees Borough Council | PF-STO-002 | Land Bridge & Highways | Active | PF-STO-002: Land Bridge & Highways
Stockton-on-Tees Borough Council | PF-STO-003 | Delivery of Active Mode Travel Infrastrcuture | Active | PF-STO-003: Delivery of Active Mode Travel Infrastrcuture
Stockton-on-Tees Borough Council | PF-STO-004 | Regeneration of Thornaby Town Centre | Active | PF-STO-004: Regeneration of Thornaby Town Centre
Stockton-on-Tees Borough Council | PF-STO-005 | Relocating NETA to Thornaby | Active | PF-STO-005: Relocating NETA to Thornaby
Stockton-on-Tees Borough Council | PF-STO-006 | Social and Community Investments in North Thornaby | Active | PF-STO-006: Social and Community Investments in North Thornaby
Stockton-on-Tees Borough Council | PF-STO-007 | Preston Park Museum & Grounds | Active | PF-STO-007: Preston Park Museum & Grounds
Stockton-on-Tees Borough Council | PF-STO-008 | Yarm High Street and Town Hall | Active | PF-STO-008: Yarm High Street and Town Hall
Stockton-on-Tees Borough Council | PF-STO-009 | Cycle Network | Active | PF-STO-009: Cycle Network
Thanet District Council | PF-THA-001 | Future High Street Fund - Creative Workspace | Active | PF-THA-001: Future High Street Fund - Creative Workspace
Thanet District Council | PF-THA-002 | Future High Street Fund - Highway Improvements | Active | PF-THA-002: Future High Street Fund - Highway Improvements
Thanet District Council | PF-THA-003 | Ramsgate LUF - Green Port Ramsgate | Active | PF-THA-003: Ramsgate LUF - Green Port Ramsgate
Thanet District Council | PF-THA-004 | Ramsgate LUF - Inclusive Harbour Attractions | Active | PF-THA-004: Ramsgate LUF - Inclusive Harbour Attractions
Thanet District Council | PF-THA-005 | Assets to Connect to Opportunity | Active | PF-THA-005: Assets to Connect to Opportunity
Thanet District Council | PF-THA-006 | Margate LUF - Margate Digital | Active | PF-THA-006: Margate LUF - Margate Digital
Thanet District Council | PF-THA-007 | Margate Town Deal - Scaling Margate's Creative Production and Skills - Margate Creative Land Trust | Active | PF-THA-007: Margate Town Deal - Scaling Margate's Creative Production and Skills - Margate Creative Land Trust
Thanet District Council | PF-THA-008 | Margate Town Deal - Scaling Margate's Creative Production and Skills - Margate Theatre Royal | Active | PF-THA-008: Margate Town Deal - Scaling Margate's Creative Production and Skills - Margate Theatre Royal
Thanet District Council | PF-THA-009 | Margate Town Deal - Coastal Wellbeing | Active | PF-THA-009: Margate Town Deal - Coastal Wellbeing
Thanet District Council | PF-THA-010 | Margate Town Deal - Active Movements and Connections | Active | PF-THA-010: Margate Town Deal - Active Movements and Connections
Thanet District Council | PF-THA-011 | Margate Town Deal - Diversifying Heritage Assets - Margate Winter Gardens | Active | PF-THA-011: Margate Town Deal - Diversifying Heritage Assets - Margate Winter Gardens
Thanet District Council | PF-THA-012 | Margate Town Deal - Diversifying Heritage Assets - Destination Dreamland | Active | PF-THA-012: Margate Town Deal - Diversifying Heritage Assets - Destination Dreamland
Thanet District Council | PF-THA-013 | Margate Town Deal Programme Management | Active | PF-THA-013: Margate Town Deal Programme Management
Wirral Council | PF-WIR-001 | Transport Visitor Attraction (Transport Shed) | Active | PF-WIR-001: Transport Visitor Attraction (Transport Shed)
Wirral Council | PF-WIR-002 | Education Engagement Network | Active | PF-WIR-002: Education Engagement Network
Wirral Council | PF-WIR-003 | Joy (Wellbeing & Opportunity Hub) | Active | PF-WIR-003: Joy (Wellbeing & Opportunity Hub)
Wirral Council | PF-WIR-004 | Egerton House | Active | PF-WIR-004: Egerton House
Wirral Council | PF-WIR-005 | Startyard | Active | PF-WIR-005: Startyard
Wirral Council | PF-WIR-006 | Future Yard Music Skills Venue | Active | PF-WIR-006: Future Yard Music Skills Venue
Wirral Council | PF-WIR-007 | Argyle Street Creative Hub | Active | PF-WIR-007: Argyle Street Creative Hub
Wirral Council | PF-WIR-008 | Sustainability Central | Active | PF-WIR-008: Sustainability Central
Wirral Council | PF-WIR-009 | Eureka! Landscaping | Active | PF-WIR-009: Eureka! Landscaping
Wirral Council | PF-WIR-010 | Woodside Ferry Village | Active | PF-WIR-010: Woodside Ferry Village
Wirral Council | PF-WIR-011 | Birkenhead Priory | Active | PF-WIR-011: Birkenhead Priory
Wirral Council | PF-WIR-012 | Hamilton Square Area Public Realm | Active | PF-WIR-012: Hamilton Square Area Public Realm
Wirral Council | PF-WIR-013 | New Ferry Housing redevelopment | Active | PF-WIR-013: New Ferry Housing redevelopment
Wirral Council | PF-WIR-014 | New Ferry Town Centre Highways and environmental improvements | Active | PF-WIR-014: New Ferry Town Centre Highways and environmental improvements
Wirral Council | PF-WIR-015 | Birkenhead Market | Active | PF-WIR-015: Birkenhead Market
Wirral Council | PF-WIR-016 | Europa Residential | Active | PF-WIR-016: Europa Residential
Wirral Council | PF-WIR-017 | Charing Cross & Grange Road | Active | PF-WIR-017: Charing Cross & Grange Road
Wirral Council | PF-WIR-018 | Conway & Europa Boulevard | Active | PF-WIR-018: Conway & Europa Boulevard
Wirral Council | PF-WIR-019 | Woodside Ferry Landing Stage | Active | PF-WIR-019: Woodside Ferry Landing Stage
Wirral Council | PF-WIR-020 | International Battle of the Atlantic | Active | PF-WIR-020: International Battle of the Atlantic
Wirral Council | PF-WIR-021 | One O Clock Gun/Woodside Bus Station | Active | PF-WIR-021: One O Clock Gun/Woodside Bus Station
Wirral Council | PF-WIR-022 | Woodside Gyratory | Active | PF-WIR-022: Woodside Gyratory
Wirral Council | PF-WIR-023 | Town Deal monitoring costs (RDEL) | Active | PF-WIR-023: Town Deal monitoring costs (RDEL)
PF-CONTROL_PROJECT-DETAILS-END

## ITValues (hidden)
Standard Outputs |  |  |  |  | Standard Outcomes
Ensure the named ranges for the Outputs are set to the Scope of the Outputs tab (not workbook). Sames for Outcomes - ensure scope is Outcomes tab, not Workbook)
Ensure the named range has the name of the theme WITH NO SPACES e.g. "employmentandeducation". These values must match exactly the values for intervention themes that the user selects on the form
Strengthening the visitor and local service economy | Employment and education | Improving the quality of life of residents | Unlocking and enabling industrial commercial and residential development | Enhancing subregional and regional connectivity | Strengthening the visitor and local service economy | Employment and education | Improving the quality of life of residents | Unlocking and enabling industrial commercial and residential development | Enhancing subregional and regional connectivity
Amount of existing hospitality space improved | Amount of new educational space created | Amount of existing parks/greenspace/outdoor improved | Amount of floor space repurposed (residential, commercial, retail) | Amount of land made wheelchair accessible/step free | Audience numbers for cultural events | There are no options to select | Change in number of properties better protected from flooding and coastal erosion | Number of major commercial planning applications granted | Change in perceived/experienced accessibility
Amount of existing retail space improved | n of full-time equivalent (FTE) permanent jobs created directly through the projects | Amount of new parks/greenspace/outdoor space | Amount of rehabilitated land | Number of alternative fuel charging/re-fuelling points | Number of anti-social behaviour crimes recorded |  | Number of anti-social behaviour crimes recorded | Number of minor commercial planning applications granted | Cycle flow
Amount of new hospitality space created | n of full-time equivalent (FTE) permanent jobs facilitated directly through the projects | Number of properties better protected from flooding and coastal erosion | Number of dilapidated buildings improved OR Number of derelict buildings refurbished | Total length of improved cycle ways | Number of crimes reported |  | Number of crimes reported | Percentage of adults who are satisfied with their local area as a place to live | Footfall
Amount of new retail space created | n of full-time equivalent (FTE) permanent jobs safeguarded directly through the projects | Number of trees planted OR Number of new trees planted |  | Total length of new cycle ways | Number of cultural events |  | Percentage of residents who report feeling safe in their local area |  | Pedestrian flow
Amount of public realm improved | n of temporary FT jobs supported during project implementation |  |  | Total length of new pedestrian paths | Number of day visitors |  |  |  | Public transport reliability
Number of heritage buildings renovated/restored OR Number of buildings renovated/restored |  |  |  | Total length of newly built roads | Number of people using a new/improved public facility |  |  |  | Vehicle flow
Number of improved community/sports centres |  |  |  | Total length of pedestrian paths improved | Number of visitors to cultural venues
Number of improved cultural facilities |  |  |  | Total length of resurfaced/improved road | Percentage of residents who report feeling safe in their local area
Number of local events or activities supported |  |  |  |  | Total consumer spending at cultural venues
Number of neighbourhood improvements undertaken |  |  |  |  | Vacancy rate of commercial units
Number of new community/sports centres
Number of new cultural facilities
Number of public amenities/facilities created
Number of public amenities/facilities improved

## Bespoke Outputs (hidden)
Selected LA in Admin tab:
Bolton Council
PF-CONTROL_BESPOKE-OUTPUTS-START
Bespoke output | UoM | Local Authority | Output | UoM | Intervention theme
Please select an option | #N/A | Bolton Council | Please select an option | #N/A | Bespoke
Amount of new office space (m2) | sqm | Bolton Council | Amount of new office space (m2) | sqm | Bespoke
Amount of capacity of new or improved training or education facilities (people) | n of | Bolton Council | Amount of capacity of new or improved training or education facilities (people) | n of | Bespoke
Amount of public realm created (sqm) | sqm | Bolton Council | Amount of public realm created (sqm) | sqm | Bespoke
% increase in participation | % | Bolton Council | % increase in participation | % | Bespoke
% increase in membership | % | Bolton Council | % increase in membership | % | Bespoke
% increase in Health Pathway referrals | % | Bolton Council | % increase in Health Pathway referrals | % | Bespoke
Number of residential units | n of | Bolton Council | Number of residential units | n of | Bespoke
Amount of new healthcare facilities sqm | sqm | Bolton Council | Amount of new healthcare facilities sqm | sqm | Bespoke
Number of new parking spaces | n of | Bolton Council | Number of new parking spaces | n of | Bespoke
Additional Learners (FE) | n of | Bolton Council | Additional Learners (FE) | n of | Bespoke
Additional Learners (HE) | n of | Bolton Council | Additional Learners (HE) | n of | Bespoke
Additional Learners (CPD) | n of | Bolton Council | Additional Learners (CPD) | n of | Bespoke
Learners moving into Healthcare from other sectors | n of | Bolton Council | Learners moving into Healthcare from other sectors | n of | Bespoke
Local employment (NHS workers living within 10 mile radious) | n of | Bolton Council | Local employment (NHS workers living within 10 mile radious) | n of | Bespoke
Number of improved community/sports centres | n of | Bolton Council | Number of improved community/sports centres | n of | Bespoke
Increase in the amount of diversity of commercial floorspace (sqm) | sqm | Bolton Council | Increase in the amount of diversity of commercial floorspace (sqm) | sqm | Bespoke
Increase in existing visits (%) | % | Bolton Council | Increase in existing visits (%) | % | Bespoke
Increase in dwell time (%) | % | Bolton Council | Increase in dwell time (%) | % | Bespoke
Increase in number of trading units | n of | Bolton Council | Increase in number of trading units | n of | Bespoke
Number of new awnings & food hall | n of | Bolton Council | Number of new awnings & food hall | n of | Bespoke
Increase in amount of shared innovation facilities (%) | % | Bolton Council | Increase in amount of shared innovation facilities (%) | % | Bespoke
Increase in amount of new specialist technology equipment (%) | % | Bolton Council | Increase in amount of new specialist technology equipment (%) | % | Bespoke
Increase in uptake of digital/technical apprenticeships (%) | % | Bolton Council | Increase in uptake of digital/technical apprenticeships (%) | % | Bespoke
Increase in the share of young people & adults who have the relevant skills for employment & entrepreneurship (%) | % | Bolton Council | Increase in the share of young people & adults who have the relevant skills for employment & entrepreneurship (%) | % | Bespoke
Increase in new business start ups (%) | % | Bolton Council | Increase in new business start ups (%) | % | Bespoke
Increase in business scale ups (%) | % | Bolton Council | Increase in business scale ups (%) | % | Bespoke
m2 of heritage buildings renovated/restored | sqm | Bolton Council | m2 of heritage buildings renovated/restored | sqm | Bespoke
Increase in no of visitors to arts, culture & heritage events | n of | Bolton Council | Increase in no of visitors to arts, culture & heritage events | n of | Bespoke
Improved perception of place (%) visitors, businesses, residents | % | Bolton Council | Improved perception of place (%) visitors, businesses, residents | % | Bespoke
Rehabilitated land m2 | sqm | Bolton Council | Rehabilitated land m2 | sqm | Bespoke
Improved parking spaces | n of | Bolton Council | Improved parking spaces | n of | Bespoke
Sites cleared | n of | Bolton Council | Sites cleared | n of | Bespoke
Additional enterprises with broadband access | n of | Bolton Council | Additional enterprises with broadband access | n of | Bespoke
Non domestic buildings with green retrofit | n of | Bolton Council | Non domestic buildings with green retrofit | n of | Bespoke
Office Space renovated/improved | sqm | Bolton Council | Office Space renovated/improved | sqm | Bespoke
Potential entrepreneurs assisted | n of | Bolton Council | Potential entrepreneurs assisted | n of | Bespoke
Closer collaboration with employers | n of | Bolton Council | Closer collaboration with employers | n of | Bespoke
Increase in capacity and accessibility to new/improved facilities | % | Bolton Council | Increase in capacity and accessibility to new/improved facilities | % | Bespoke
|  | Calderdale Council | You have no bespoke outputs to select | #N/A | Bespoke
|  | City of Wolverhampton Council | Please select an option | #N/A | Bespoke
|  | City of Wolverhampton Council | People supported into employment | n of | Bespoke
|  | City of Wolverhampton Council | People sustaining in employment at 12 weeks | n of | Bespoke
|  | City of Wolverhampton Council | New employment opportunities created | n of | Bespoke
|  | City of Wolverhampton Council | Number of new or improved car parking spaces | n of | Bespoke
|  | City of Wolverhampton Council | # of learners/trainees/students enrolled at new/improved education and training facilities | n of | Bespoke
|  | City of Wolverhampton Council | Change in air quality % | % | Bespoke
|  | City of Wolverhampton Council | Cycle usage increase % | % | Bespoke
|  | City of Wolverhampton Council | Number of people using new/improved public facility | n of | Bespoke
|  | City of Wolverhampton Council | Number of closer collaborations with employers | n of | Bespoke
|  | City of Wolverhampton Council | Total fibre optic cable ducting (km) | km | Bespoke
|  | City of Wolverhampton Council | Total new Event space created (sqm) | sqm | Bespoke
|  | City of Wolverhampton Council | Total number of new bus stops | n of | Bespoke
|  | City of Wolverhampton Council | Number of residential units improved/refurbished | n of | Bespoke
|  | City of Wolverhampton Council | Number of enterprises receiving non-financial support | n of | Bespoke
|  | City of Wolverhampton Council | Amount of floor space rationalised sqm | sqm | Bespoke
|  | City of Wolverhampton Council | Total m2 existing educational space improved | sqm | Bespoke
|  | City of Wolverhampton Council | number of cleared sites | n of | Bespoke
|  | Lewes District Council | Please select an option | #N/A | Bespoke
|  | Lewes District Council | Amount of public realm improved | sqm | Bespoke
|  | Lewes District Council | Amount of new office space | sqm | Bespoke
|  | Lewes District Council | # of leaders /trainees/students enrolled at new education and training facilities | n of | Bespoke
|  | Lewes District Council | Amount of capacity of new or improved training or education facilities | n of | Bespoke
|  | Lewes District Council | # of enterprises receiving grants | n of | Bespoke
|  | Lewes District Council | Number of non-domestic buildings with green retrofits completed | n of | Bespoke
|  | Lewes District Council | Amount of office space renovated/improved | sqm | Bespoke
|  | Lewes District Council | # of learners enrolled in new education and training courses | n of | Bespoke
|  | Lewes District Council | Number of alternative fuel charging / refuelling points | n of | Bespoke
|  | Nuneaton & Bedworth Borough Council | Please select an option | #N/A | Bespoke
|  | Nuneaton & Bedworth Borough Council | Amount of new public realm (m2 of land) | sqm | Bespoke
|  | Nuneaton & Bedworth Borough Council | Number of improved car parking spaces (Number) | n of | Bespoke
|  | Nuneaton & Bedworth Borough Council | Number of residential units provided (Number) | n of | Bespoke
|  | Nuneaton & Bedworth Borough Council | Availability of new specialist equipment (Number) | n of | Bespoke
|  | Nuneaton & Bedworth Borough Council | Improved perceptions of the place by residents/businesses/ visitors (Percentage) | % | Bespoke
|  | Nuneaton & Bedworth Borough Council | Increase in the amount of shared workspace and innovation facilities (Number) | n of | Bespoke
|  | Nuneaton & Bedworth Borough Council | Increased benefit for public education over the longer term (Number) | n of | Bespoke
|  | Nuneaton & Bedworth Borough Council | New apprentices (Number) | n of | Bespoke
|  | Nuneaton & Bedworth Borough Council | New volunteers (Number) | n of | Bespoke
|  | Nuneaton & Bedworth Borough Council | Number of job ready learners (Number) | n of | Bespoke
|  | Nuneaton & Bedworth Borough Council | Number of new leaners assisted (Number) | n of | Bespoke
|  | Nuneaton & Bedworth Borough Council | Number of visitors to arts, cultural and heritage events and venues (Number) | n of | Bespoke
|  | Nuneaton & Bedworth Borough Council | Percent of working-age population with qualifications (Percentage) | % | Bespoke
|  | Rotherham Metropolitan Borough Council | Please select an option | #N/A | Bespoke
|  | Rotherham Metropolitan Borough Council | Number of sites cleared (#) | n of | Bespoke
|  | Rotherham Metropolitan Borough Council | Amount of new office space (m2) | sqm | Bespoke
|  | Rotherham Metropolitan Borough Council | Amount of office space renovated/improved (m2) | sqm | Bespoke
|  | Rotherham Metropolitan Borough Council | Number of new residential units (#) | n of | Bespoke
|  | Rotherham Metropolitan Borough Council | Remediation and/or development of abandoned or dilapidated sites (m2) | sqm | Bespoke
|  | Rotherham Metropolitan Borough Council | Increase in the amount (& diversity) of high quality, affordable commercial floorspace (m2) | sqm | Bespoke
|  | Rotherham Metropolitan Borough Council | Delivery of new public spaces (m2) | sqm | Bespoke
|  | Rotherham Metropolitan Borough Council | Land acquired for mainline station delivery (m2) | sqm | Bespoke
|  | Rotherham Metropolitan Borough Council | Number of sites brought into public ownership (#) | n of | Bespoke
|  | Rotherham Metropolitan Borough Council | Amount of new retail, leisure or food & beverage space (m2) | sqm | Bespoke
|  | Rotherham Metropolitan Borough Council | Amount of new public realm created (m2) | sqm | Bespoke
|  | Rotherham Metropolitan Borough Council | Amount of new 'other' enterprise space (m2) | sqm | Bespoke
|  | Rotherham Metropolitan Borough Council | Number of buildings acquired (#) | n of | Bespoke
|  | Rotherham Metropolitan Borough Council | Area of sites acquired (m2) | sqm | Bespoke
|  | Rotherham Metropolitan Borough Council | Land secured for new or upgraded cycle or walking paths (m2) | sqm | Bespoke
|  | Rotherham Metropolitan Borough Council | Delivery of quality residential or commercial space in key locations (m2) | sqm | Bespoke
|  | Rotherham Metropolitan Borough Council | Land acquired/de-risked for residential development (#) | sqm | Bespoke
|  | Rotherham Metropolitan Borough Council | Amount of improved cultural space completed (m2) | sqm | Bespoke
|  | Rotherham Metropolitan Borough Council | Amount of floorspace repurposed (m2) | sqm | Bespoke
|  | Sheffield City Council | Please select an option | #N/A | Bespoke
|  | Sheffield City Council | # new or improved parking spaces | n of | Bespoke
|  | Sheffield City Council | # of new Wayfinding Infrastructure | n of | Bespoke
|  | Sheffield City Council | # of new Cycle storage hub | n of | Bespoke
|  | Sheffield City Council | Public Education Infrasture, Info panels | n of | Bespoke
|  | Sheffield City Council | Increase in local skills, Volunteers trained and Assisted | n of | Bespoke
|  | Sheffield City Council | Increase in local skills, new learners assisted | n of | Bespoke
|  | Sheffield City Council | Improved public space alongside river, KM | km | Bespoke
|  | Sheffield City Council | Remediation of dilapidated site, M2 of Land | sqm | Bespoke
|  | Sheffield City Council | # new all wheels Facility | n of | Bespoke
|  | Sheffield City Council | # of new public transport routes | n of | Bespoke
|  | Sheffield City Council | Amount of new public realm, M2 land | sqm | Bespoke
|  | Sheffield City Council | Upgraded Shop Frontages (grants) | n of | Bespoke
|  | Sheffield City Council | Upgraded Shop Frontages (through scheme) | n of | Bespoke
|  | Sheffield City Council | Amount of new office space, m2 floor apce | sqm | Bespoke
|  | Sheffield City Council | Amount of capacity of new or improved training or education facilities, # people | n of | Bespoke
|  | Sheffield City Council | Amount of new 'other' enterprise space, m2 floorspace | sqm | Bespoke
|  | Sheffield City Council | New Hydrotherapy Pool | n of | Bespoke
|  | Sheffield City Council | Developing an artificial all weather 3G pitch to be available for team sports including football and rugby. | n of | Bespoke
|  | Sheffield City Council | The development of a Sports Pavilion for both cricket and football. | n of | Bespoke
|  | Sheffield City Council | Playing pitch and access improvements to the Rugby Club ground. | n of | Bespoke
|  | Sheffield City Council | # of learners/trainees/students enrolled at improved education and training facilities | n of | Bespoke
|  | Sheffield City Council | Amount of new healthcare space created, m2 | sqm | Bespoke
|  | Sheffield City Council | Number of sites cleared | n of | Bespoke
|  | Sheffield City Council | Length of new cycling and walking route | km | Bespoke
|  | Sheffield City Council | Length of improved cycling and walking route | km | Bespoke
|  | Sheffield City Council | Amount of existing 'other' non-residential space (not captured elsewhere) improved | sqm | Bespoke
|  | Stockton-on-Tees Borough Council | Please select an option | #N/A | Bespoke
|  | Stockton-on-Tees Borough Council | residential units provided | n of | Bespoke
|  | Stockton-on-Tees Borough Council | number of sites cleared | n of | Bespoke
|  | Stockton-on-Tees Borough Council | number of learners enrolled in new education and training courses | n of | Bespoke
|  | Stockton-on-Tees Borough Council | number of residential units improved/refurbished | n of | Bespoke
|  | Stockton-on-Tees Borough Council | Amount of capacity of new or improved training or education facilities | sqm | Bespoke
|  | Stockton-on-Tees Borough Council | Number of learners/trainees/students gaining certificates, graduating or completing courses at new or improved training or education facilities or attending new courses | n of | Bespoke
|  | Stockton-on-Tees Borough Council | Number of learners/trainees/students enrolled at improved education and training facilities | n of | Bespoke
|  | Stockton-on-Tees Borough Council | Number of sites cleared | n of | Bespoke
|  | Stockton-on-Tees Borough Council | Amount of Floor Space Ratinalised (Sqm) | sqm | Bespoke
|  | Stockton-on-Tees Borough Council | Amount of new office space | sqm | Bespoke
|  | Stockton-on-Tees Borough Council | Amount of office space renovated/ improved | sqm | Bespoke
|  | Stockton-on-Tees Borough Council | Amount of new cultural space created | sqm | Bespoke
|  | Thanet District Council | You have no bespoke outputs to select | #N/A | Bespoke
|  | Wirral Council | Please select an option | #N/A | Bespoke
|  | Wirral Council | Amount of new 'other' enterprise space (not captured by the other categories) | sqm | Bespoke
|  | Wirral Council | # of transport nodes with new multimodal connection points | n of | Bespoke
|  | Wirral Council | Number of type of public transport improvements | n of | Bespoke
|  | Wirral Council | # of residential units provided | n of | Bespoke
|  | Wirral Council | Total length of road converted to cycling or pedestrian way (km) | km | Bespoke
|  | Wirral Council | # of sites cleared | n of | Bespoke
|  | Wirral Council | # New Primary Substation | n of | Bespoke
|  | Wirral Council | Acquisition of House of Fraser | n of | Bespoke
|  | Wirral Council | Area of heritage buildings restored (m2) | sqm | Bespoke
|  | Wirral Council | Number of new or improved car parking spaces | n of | Bespoke
PF-CONTROL_BESPOKE-OUTPUTS-END

## Bespoke Outcomes (hidden)
Selected LA in Admin tab:
Bolton Council
PF-CONTROL_BESPOKE-OUTCOMES-START
Bespoke outcome | UoM | Local Authority | Outcome | UoM | Intervention theme
Please select an option | #N/A | Bolton Council | Please select an option | #N/A | Bespoke
Travel times in corridors of interest | % | Bolton Council | Travel times in corridors of interest | % | Bespoke
Number of enterprises receiving non financial support | n of | Bolton Council | Number of enterprises receiving non financial support | n of | Bespoke
No of births of new enterprises | n of | Bolton Council | No of births of new enterprises | n of | Bespoke
Average occupany rates work spaces (5) | n of | Bolton Council | Average occupany rates work spaces (5) | n of | Bespoke
(%) of adults satisfied with their area | % | Bolton Council | (%) of adults satisfied with their area | % | Bespoke
(%) of visitors likely to recommend the town | % | Bolton Council | (%) of visitors likely to recommend the town | % | Bespoke
No of people using an improved/new public facility (%) | n of | Bolton Council | No of people using an improved/new public facility (%) | n of | Bespoke
(%) of customers or visitors who report a positive experience | % | Bolton Council | (%) of customers or visitors who report a positive experience | % | Bespoke
|  | Calderdale Council | You have no bespoke outcomes to select | #N/A | Bespoke
|  | City of Wolverhampton Council | Please select an option | #N/A | Bespoke
|  | City of Wolverhampton Council | Estimated carbon dioxide equivalent reductions as a result of support (tonnes) | n of | Bespoke
|  | City of Wolverhampton Council | New residential units | n of | Bespoke
|  | Lewes District Council | You have no bespoke outcomes to select | #N/A | Bespoke
|  | Nuneaton & Bedworth Borough Council | Please select an option | #N/A | Bespoke
|  | Nuneaton & Bedworth Borough Council | Change in Footfall - year on year % change in monthly footfall (Percentage) | % | Bespoke
|  | Nuneaton & Bedworth Borough Council | Electric Vehicle uptake (Number) | n of | Bespoke
|  | Nuneaton & Bedworth Borough Council | Increase in capacity and accessibility to new or improved skills facilities (Number) | n of | Bespoke
|  | Nuneaton & Bedworth Borough Council | Increase in the breadth of the local skills offer that responds to local needs (Number) | n of | Bespoke
|  | Nuneaton & Bedworth Borough Council | New community hub, space, asset with links to local growth (number) | n of | Bespoke
|  | Nuneaton & Bedworth Borough Council | Numbef of job ready learners (Number) | n of | Bespoke
|  | Nuneaton & Bedworth Borough Council | Numbef of visitors to arts, cultural and heritage events and venues (Number) | n of | Bespoke
|  | Nuneaton & Bedworth Borough Council | Number of enterprises assisted (Number) | n of | Bespoke
|  | Nuneaton & Bedworth Borough Council | Number of new learners assisted (Number) | n of | Bespoke
|  | Nuneaton & Bedworth Borough Council | Number of start ups (Number) | n of | Bespoke
|  | Nuneaton & Bedworth Borough Council | Pecentage of adults who are considered "active" (Percentage) | % | Bespoke
|  | Nuneaton & Bedworth Borough Council | Percentage of childen and young people who are considered "active" (Percentage) | % | Bespoke
|  | Rotherham Metropolitan Borough Council | Please select an option | #N/A | Bespoke
|  | Rotherham Metropolitan Borough Council | Number of students enrolling in Further Education courses (#) | n of | Bespoke
|  | Rotherham Metropolitan Borough Council | Number of students completing Further Education courses (#) | n of | Bespoke
|  | Rotherham Metropolitan Borough Council | Reducing the town centre vacancy rate (%) | % | Bespoke
|  | Rotherham Metropolitan Borough Council | Reduce Crime Rates & ASB in the Town Centre (%) | % | Bespoke
|  | Sheffield City Council | Please select an option | #N/A | Bespoke
|  | Sheffield City Council | Patronage of the public transport system in the area of interest (for public transport schemes) | n of | Bespoke
|  | Sheffield City Council | Percentage of customers/visitors/users who report a positive experience | % | Bespoke
|  | Sheffield City Council | Better training & education opportunities in CAH sector | n of | Bespoke
|  | Sheffield City Council | Improved perception of area | % | Bespoke
|  | Sheffield City Council | National and international profile of Sheffield and City Region increases, press articles | % | Bespoke
|  | Sheffield City Council | Population reconnected to heritage | n of | Bespoke
|  | Sheffield City Council | Business investment, £ | £ | Bespoke
|  | Sheffield City Council | Business sentiment, % | % | Bespoke
|  | Stockton-on-Tees Borough Council | Please select an option | #N/A | Bespoke
|  | Stockton-on-Tees Borough Council | Number of students enrolled in Furthur Education | n of | Bespoke
|  | Stockton-on-Tees Borough Council | Number of residential/ domestic units upgraded to APC rating C or above | n of | Bespoke
|  | Thanet District Council | You have no bespoke outcomes to select | #N/A | Bespoke
|  | Wirral Council | You have no bespoke outcomes to select | #N/A | Bespoke
PF-CONTROL_BESPOKE-OUTCOMES-END