## Metadata
Reporting Round | Fund Name
2 | Towns Fund

## Start
Pathfinders Reporting Template
PF-USER_CURRENT-REPORTING-PERIOD-START
Reporting period
Q2 2024/25: Jul 2024 - Sep 2024
PF-USER_CURRENT-REPORTING-PERIOD-END
Sections in this template
Admin
Provide key dates, the name of your organisation, and contact details.
Progress
Provide the information on the delivery of your portfolio which include spend and delivery RAG ratings for each project, issues, and key upcoming milestones.
Project location
Provide the postcode or postcodes associated with each project.
Outputs
Provide outputs for various intervention themes. Standard and bespoke outputs are supported.
Outcomes
Provide outcomes for various intervention themes. Standard and bespoke outcomes are supported.
Finances
Provide committed and forecast spend at both portfolio and project level, and plans for uncommitted funding, or underspend.
Risks
List the top five risks across your portfolio and their mitigations.
Sign off
Section 151 Officer or Chief Finance Officer to sign off the template before submission.
Reporting Period
<Select>
April 2023 to Sept 2023
Oct 2023 to March 2024
April 2024 to Sept 2024
Sept 2024 to Feb 2025

## Admin
Admin
PF-USER_FINANCIAL-COMPLETION-DATE-START
Financial completion date
Date by which portfolio grant funding will be defrayed by Local Authority.
31st March 2026
PF-USER_FINANCIAL-COMPLETION-DATE-END
PF-USER_ACTIVITY-END-DATE-START
Activity end date
Date by which all of the physical project activity will be completed.
31st March 20280
PF-USER_ACTIVITY-END-DATE-END
PF-USER_PRACTICAL-COMPLETION-DATE-START
Practical completion date
Date by which Pathfinder grant elements of projects will be physically complete and all Pathfinder portfolio outputs achieved.
31st March 2030
PF-USER_PRACTICAL-COMPLETION-DATE-END
PF-USER_ORGANISATION-NAME-START
Organisation name | Fund Type 1 | Place Name A
Test Council
PF-USER_ORGANISATION-NAME-END
Who is the best person to contact about this return?
PF-USER_CONTACT-NAME-START
Contact name
Tester McTestface
PF-USER_CONTACT-NAME-END
PF-USER_CONTACT-EMAIL-START
Contact email | Fund Type 3 | Place Name C
tester.mctestface@communities.gov.uk
PF-USER_CONTACT-EMAIL-END
PF-USER_CONTACT-TELEPHONE-START
Contact telephone | Fund Type 4 | Place Name D
This field is optional
7775123456
PF-USER_CONTACT-TELEPHONE-END |  | Place Name F
Place Name G
Place Name H
Place Name I
Place Name J
Place Name K
Place Name L
Place Name M
Place Name N
Place Name O
Place Name P
Place Name Q
Place Name R

## Progress
Progress
Portfolio level RAG rating
Please provide overall RAG ratings for your portfolio-level spend and delivery.
PF-USER_PORTFOLIO-RAG-RATINGS-START | PF-USER_PORTFOLIO-RAG-RATING-START | PF-USER_PORTFOLIO-RAG-RATING-START | PF-USER_PORTFOLIO-RAG-RATING-START
Statement |  |  | RAG rating
Your ability to spend the current spending profile |  |  | Green
Your current portfolio-level delivery progress |  |  | Please select an option
PF-USER_PORTFOLIO-PROGRESS-START |  |  |  | PF-USER_PORTFOLIO-RAG-RATINGS-END
Portfolio progress
How is the delivery of your portfolio progressing? • Please provide a portfolio-level summary of the last financial quarter, together with more detailed updates on individual projects as required. This could be where a greater level of progress has been made, or challenges have affected delivery and/or defrayal of Pathfinder funds, particularly where holistic delivery is concerned, i.e. projects are contingent on others meeting milestones etc. • For projects where RAG ratings have increased since the previous monitoring return, we expect to see additional narrative to provide clarity and justification. • For significant challenges on projects across the portfolio, please utilise the section below on big issues across portfolio to provide further detail.
Across the portfolio projects are either completed or are nearing completion. Only the Streets for All projects is behind schedule whilst design issues have been addressed. This project is the first in a programme that will be delivered across xxx so establish design principles has been a fundamental isue and has taken longer than anticipated. However the fist of two phases has been tendered and work is due to start imminently. Future High Fund allocations are being prioritised for early spend and this is reflected in the financial forecasts. The construction phase of the xxx project is nearing completion, fit out will follow over the summer with operations beginning in early autumn. The xxx Institute of xxx will receive its first cohort of fulltime students in September. Some short courses have already been run from the building. The xxx Market Precinct project has made excellent progress over the past quarter with the main residential blocks built to roof height. The community hub buildig is progressing with the Council expecting to finalise the head lease during the summer ahead of final completion in xxx 2024. Work is continuing on the improvements to the public realm in xxx Town centre with the environment in the vicinty of xxx Park underway. Scheme costs are less than expected in some cases. xxx Museum and Library, xxx Market and xxx Leisure Centre are now complete and operational.
500 words suggested |  |  |  | PF-USER_PORTFOLIO-PROGRESS-END
Project progress
Spend Risk |  |  |  | Delivery Risk
The table below is for illustrative guidance purposes only and the examples given are not intended to cover all potiential project scenarios. It is not an exhaustive list and only intended as a prompt for some of the things you might consider when RAG (red, amber, green) scoring the spend and delivery risks associated with your individual projects. You should rate each project based on your own knowledge of the individual circumstances influencing both spend and delivery risk. Use the narrative box to provide further explanation.
Enter a spend RAG rating for each project and some explanatory narrative so we understand where you might need some support. To help you choose a rating, examples of what each rating might include are below. Green: no rising costs, no slippage, less than 30% expenditure profiled in final year, no use of financial flexibility. Amber/Green: project progressing but with minor issues identified, issues are within control of LA and there is a mitigation plan in place, the appropriate RIBA stage has minor slippage but a mitigation plan is in place, there is no additional support required. Amber: cost increases (10 to 20%) which are manageable, a funding gap exists but a source has been identified although not secured, there is slippage between 20% to 30% between financial years, 40% to 50% of expenditure is profiled in final year, the use of financial flexibilities is required but below threshold. Amber/Red: the project has stalled for any reason, Value Engineering is required or in progress due to significant cost increases or over-runs, significant additional match funding required to facilitate delivery, potential match funding source identified but not secured. Red: major cost increases over 30% which is un-manageable and there is no plan in place to resolve the problem, there is major slippage over 40% between financial years, over 60% of expenditure is profiled in final year, major movement of funding planned, major additional match funding required to facilitate delivery, match funding source not identified, call in required. |  |  |  | Enter a delivery RAG rating for each project and some explanatory narrative. This tells us where you might need support, and where we can celebrate success. Green: planning is in place, main contract procurement process complete, delivery milestones on target, appropriate RIBA stage on track, project completed. Amber/Green: project is progressing but minor issues identified (these are within control of LA and there is a plan in place), the appropriate RIBA stage has minor slippage but there is a plan in place to deal with the issue, no additional support required. Amber: the project progressing but delayed, the issues identified are within control of LA but there is currently no plan in place to deal with the issue, Value Engineering is required or in progress, the appropriate RIBA stage has slipped considerably, additional support required. Amber/Red: the project has stalled, Value Engineering is required or in progress and likely to result in a new planning application and delayed delivery timelines, major RIBA stage slippage, major additional support required. Red: project stalled, issues out of LA control, major support required, major RIBA stage slippage, no plan in place.
PF-USER_PROJECT-PROGRESS-START
Project name | Project status | Spend RAG rating | Delivery RAG rating | Why have you given these ratings? Enter an explanation (100 words max)
Please select an option
PF-ANO-001: Anon Innovation Hub | In progress | Amber/Green | Amber/Green | Work is underway but slightly behind schedule. A plan to recover lost time is being prepared but there is a risk that completion may slip by c 3 weeks to mid July 2024.. The building is still expected to be operational from 1st September and management agreement are progresasing well.
PF-ANO-002: Anon Market Upgrades | Project complete | Green | Green | Food hall opened March 2024
PF-ANO-003: Anon Library & Museum Upgrade | Project complete | Green | Green | Completed November 2023
PF-ANO-004: Public Realm Improvements | In progress | Amber/Green | Amber/Green
PF-ANO-005: Accelerated Funding £1 million Public Realm Improvements | Project complete | Green | Green | Completed
PF-ANO-006: Anon Market Precinct | In progress | Amber/Green | Amber/Green | FHSF funding fully defrayed March 2024, construction work funded by xxx on target for completion November 2024
PF-ANO-007: Anon Leisure Centre Expansion | Project complete | Green | Green | Opened April 2023
PF-ANO-008: Streets for All - Anon | In progress | Amber/Green | Amber/Green | Phase 1 to start on site April 2024 to be completed April 2025, Phase 2 start April 2025m completion 2026. FHSF extension requested , Profile change to be recorded (less than £5m)
PF-ANO-009: Anon College of Medical Science | Project complete | Green | Green | Building work completed, first full time student intake September 2024
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
| Please select an option | Please select an option | Please select an option
PF-USER_PROJECT-PROGRESS-END
PF-USER_BIG-ISSUES-ACROSS-PORTFOLIO-START
Big issues across portfolio
Tell us about the issues affecting delivery of your projects. We use this information to see how we might be able to help. • Expand on any spend/delivery issues highlighted in the above sections, providing rationale for how the issue(s) has materialised. Please include what stage project delivery is at, what action is being taken to mitigate the issue(s), estimated resolution date (if possible) and how this will affect individual project milestones, including the March 2026 deadline for completion. • Please indicate whether a PAR is/will be required. • Where there is a variance on the Outputs and Outcomes tabs between the baseline data and the MR data, please include narrative in this section for the variance.
The majority of current projects are either completed or nearing completion. Start on the xxx project has been delayed whilst design issues were resolved. However work is expected to start on site this month and both phases of the project scheduled for completion in March 2026. LUF3 projects are undergoing validation and are expected to be added to the portfolio in due course.
500 words suggested |  |  |  | PF-USER_BIG-ISSUES-ACROSS-PORTFOLIO-END
PF-USER_UPCOMING-SIGNIFICANT-MILESTONES-START
Upcoming significant milestones
What significant milestones are coming up? We use this information to find communication opportunities. For example, we might highlight your successes to others, write about them in a case study, or organise a ministerial visit.
The first full student intake at xxx Institue of xxx will take place in September and the xxx project is scheduled for completion in late Summer/early autumn 2024.
500 words suggested |  |  |  | PF-USER_UPCOMING-SIGNIFICANT-MILESTONES-END

## Project location
Project location
PF-USER_PROJECT-LOCATION-START
Project name | Project full postcode/postcodes (for example, AB1D 2EF)
If a project has multiple postcodes, enter postcodes with a comma separating each one (for example, AB1D 2EF, WC1 3RJ).
PF-ANO-001: Anon Innovation Hub | BL1 1US
PF-ANO-002: Anon Market Upgrades | BL1 1TQ
PF-ANO-003: Anon Library & Museum Upgrade | BL1 1SE
PF-ANO-004: Public Realm Improvements | BL1 1UR, BL1 1TQ, BL1 1SU
PF-ANO-005: Accelerated Funding £1 million Public Realm Improvements | BL1 1UR, BL1 1TQBL1 1SUD
PF-ANO-006: Anon Market Precinct | BL4 7AF
PF-ANO-007: Anon Leisure Centre Expansion | BL4 9DZ
PF-ANO-008: Streets for All - Anon | BL4 8HP, BL4 8AQ, BL4 9AJ, BL4 8HQ, BL4 9BB, BL4 7NS, BL4 7NY, BL4 7FU, BL4 8EX, BL4 9AE, BL4 7PD
PF-ANO-009: Anon College of Medical Science | BL4 0JR
PF-USER_PROJECT-LOCATION-END

## Outputs
Outputs
What have you delivered, and what is forecast to be delivered?
Tell us about the outputs you are delivering and the outcomes these are achieving, or expected to achieve. Provide this at portfolio level by intervention theme. Investment themes have been developed to help MHCLG evaluate how our funds are helping to achieve Levelling Up. Investment themes are designed to organise outputs and outcomes by the objective of the project rather than the nature of the activities being undertaken. This is because similar projects can have different objectives and different activities can achieve the same result. For example, road improvements can facilitate development by linking a site to the road network or strengthen the service economy by making it easier to access a visitor attraction. When selecting an investment theme, think about the main long term objective of delivering the output or outcome.
Description of investment themes
Intervention theme | Description
Improving quality of life for residents | Projects where the principal aim is to improve the quality of life of residents by improving the quality of local public services and associated infrastructure. Projects funded under this heading are diverse: including improvements to educational, health, leisure and community facilities, environmental amenities (for example, parks), investments in new or improved social housing stock, and provisioning of cycling and walking infrastructure.
Strengthening the local service economy | Projects aiming to support economic regeneration via stimulating greater levels of consumer spending in local economies. These include investments in culture or heritage assets that serve as visitor attractions, investments in the public realm (for example, town centre improvement projects or enhancements to other infrastructure to improve the visitor experience), and provisioning of new or improved retail floorspace.
Unlocking commercial, industrial and residential development | Projects aiming to support economic regeneration or accommodate economic growth by unlocking or enabling the development of brownfield or greenfield for employment or residential uses. These projects would include direct investments in property development, investments in land reclamation or remediation, as well as the provisioning of site services (including access roads) to enable their onward development.
Enhancing regional and subregional connectivity | Projects aiming to improve connectivity between areas by creating new routes between areas, reducing congestion, or otherwise reducing journey times. These include direct investments in new or improved road or rail links, as well as enhancements to other forms of public transport. Active travel projects, such as new or improved cyclepaths and walkways should be categorised as improving quality of life.
Employment and education | Projects that aim to improve the level of skills attainment by increasing access to education, training and career opportunities. These include support for businesses to create jobs, new or improved education, community, and leisure facilities to be used for learning and developing skills.
Standard outputs
PF-USER_STANDARD-OUTPUTS-START
Intervention theme | Output | Unit of measurement | Baseline output | Total cumulative outputs to date |  | Financial year 2024 to 2025 |  |  |  |  | Financial year 2025 to 2026 |  |  |  |  | April 2026 and after | Grand total | Variance % (Between MR and Baseline)
|  |  |  | (Up to and including Mar 2024) | Total | (Apr to Jun) | (Jul to Sep) | (Oct to Dec) | (Jan to Mar) | Total | (Apr to Jun) | (Jul to Sep) | (Oct to Dec) | (Jan to Mar) | Total | Total
|  |  |  | Actual |  | Actual | Actual | Forecast | Forecast |  | Forecast | Forecast | Forecast | Forecast
Enhancing subregional and regional connectivity | Total length of pedestrian paths improved | km | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 | 0.6 | 0 | 0 | 0 | 1.5 | 1.5 | 0 | 2.1 | 0%
Enhancing subregional and regional connectivity | Total length of new pedestrian paths | km | 4.39 | 2.22 | 2.22 | 0 | 0 | 2.17 | 0 | 2.17 | 0 | 0 | 0 | 0 | 0 | 0 | 4.39 | 2.023e-14%
Enhancing subregional and regional connectivity | Total length of new cycle ways | km | 4.39 | 0 | 0 | 0 | 0 | 0 | 4.39 | 4.39 | 0 | 0 | 0 | 0 | 0 | 0 | 4.39 | -0%
Enhancing subregional and regional connectivity | Total length of improved cycle ways | km | 5.05 | 0 | 0 | 0 | 0 | 0 | 5.05 | 5.05 | 0 | 0 | 0 | 0 | 0 | 0 | 5.05 | -0%
Enhancing subregional and regional connectivity | Total length of resurfaced/improved road | km | 2.38 | 0 | 0 | 0 | 0 | 0 | 2.38 | 2.38 | 0 | 0 | 0 | 2.38 | 2.38 | 0 | 4.76 | 100%
Enhancing subregional and regional connectivity | Total length of newly built roads | km | 0.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -100%
Enhancing subregional and regional connectivity | Number of alternative fuel charging/re-fuelling points | n of | 18 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | -0%
Enhancing subregional and regional connectivity | Amount of land made wheelchair accessible/step free | sqm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Unlocking and enabling industrial commercial and residential development | Amount of rehabilitated land | sqm | 32500 | 8200 | 8200 | 0 | 0 | 0 | 10800 | 10800 | 0 | 0 | 0 | 0 | 0 | 0 | 19000 | -41.54%
Unlocking and enabling industrial commercial and residential development | Number of dilapidated buildings improved OR Number of derelict buildings refurbished | n of | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -0%
Unlocking and enabling industrial commercial and residential development | Amount of floor space repurposed (residential, commercial, retail) | sqm | 2900 | 2900 | 2900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2900 | -0%
Strengthening the visitor and local service economy | Amount of public realm improved | sqm | 3504 | 0 | 0 | 0 | 0 | 0 | 3504 | 3504 | 0 | 0 | 0 | 0 | 0 | 0 | 3504 | -0%
Strengthening the visitor and local service economy | Number of public amenities/facilities created | n of | 2 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | -0%
Strengthening the visitor and local service economy | Number of public amenities/facilities improved | n of | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -0%
Strengthening the visitor and local service economy | Amount of new retail space created | sqm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Strengthening the visitor and local service economy | Amount of existing retail space improved | sqm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Strengthening the visitor and local service economy | Amount of new hospitality space created | sqm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Strengthening the visitor and local service economy | Amount of existing hospitality space improved | sqm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Strengthening the visitor and local service economy | Number of local events or activities supported | n of | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Strengthening the visitor and local service economy | Number of new community/sports centres | n of | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -100%
Strengthening the visitor and local service economy | Number of neighbourhood improvements undertaken | n of | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Strengthening the visitor and local service economy | Number of heritage buildings renovated/restored OR Number of buildings renovated/restored | n of | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -0%
Strengthening the visitor and local service economy | Number of improved cultural facilities | n of | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | -0%
Strengthening the visitor and local service economy | Number of improved community/sports centres | n of | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -0%
Strengthening the visitor and local service economy | Number of new cultural facilities | n of | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Improving the quality of life of residents | Number of trees planted OR Number of new trees planted | n of | 103 | 45 | 45 | 0 | 0 | 0 | 49 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | -8.738%
Improving the quality of life of residents | Amount of existing parks/greenspace/outdoor improved | sqm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Improving the quality of life of residents | Amount of new parks/greenspace/outdoor space | sqm | 3048 | 3400 | 3400 | 0 | 0 | 0 | 3048 | 3048 | 0 | 0 | 0 | 0 | 0 | 0 | 6448 | 111.5%
Improving the quality of life of residents | Number of properties better protected from flooding and coastal erosion | n of | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Employment and education | n of full-time equivalent (FTE) permanent jobs created directly through the projects | n of | 835 | 326 | 326 | 10 | 10 | 10 | 59 | 89 | 2 | 2 | 2 | 60 | 66 | 354 | 835 | -0%
Employment and education | n of full-time equivalent (FTE) permanent jobs safeguarded directly through the projects | n of | 10003 | 0 | 0 | 375 | 375 | 375 | 2375 | 3500 | 500 | 500 | 500 | 2000 | 3500 | 3003 | 10003 | -0%
Employment and education | n of full-time equivalent (FTE) permanent jobs facilitated directly through the projects | n of | 1304 | 0 | 0 | 50 | 50 | 50 | 359 | 509 | 30 | 30 | 30 | 30 | 120 | 675 | 1304 | -0%
Employment and education | n of temporary FT jobs supported during project implementation | n of | 381 | 236 | 236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 236 | -38.06%
Employment and education | Amount of new educational space created | sqm | 6800 | 6800 | 6800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6800 | -0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
[18 empty] | PF-USER_STANDARD-OUTPUTS-END | n of
Bespoke outputs
PF-USER_BESPOKE-OUTPUTS-START
Intervention theme | Output | Unit of measurement | Baseline output | Total cumulative outputs to date |  | Financial year 2024 to 2025 |  |  |  |  | Financial year 2025 to 2026 |  |  |  |  | April 2026 and after | Grand total | Variance % (Between MR and Baseline)
|  |  |  | (Up to and including Mar 2024) | Total | (Apr to Jun) | (Jul to Sep) | (Oct to Dec) | (Jan to Mar) | Total | (Apr to Jun) | (Jul to Sep) | (Oct to Dec) | (Jan to Mar) | Total | Total
|  |  |  | Actual |  | Actual | Actual | Forecast | Forecast |  | Forecast | Forecast | Forecast | Forecast
Bespoke | Amount of new office space (m2) | sqm | 370 | 0 | 0 | 0 | 0 | 0 | 370 | 370 | 0 | 0 | 0 | 0 | 0 | 0 | 370 | 0%
Bespoke | Amount of capacity of new or improved training or education facilities (people) | n of | 557 | 557 | 557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6800 | 7357 | 1221%
Bespoke | Amount of public realm created (sqm) | sqm | 7279 | 450 | 450 | 200 | 0 | 0 | 1516 | 1716 | 0 | 0 | 0 | 3704 | 3704 | 0 | 5870 | -19.36%
Bespoke | % increase in participation | % | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | -0%
Bespoke | % increase in membership | % | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | -0%
Bespoke | % increase in Health Pathway referrals | % | 40 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | -0%
Bespoke | Number of residential units | n of | 98 | 0 | 0 | 0 | 0 | 0 | 98 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | -0%
Bespoke | Amount of new healthcare facilities sqm | sqm | 6800 | 0 | 0 | 6800 | 0 | 0 | 0 | 6800 | 0 | 0 | 0 | 0 | 0 | 0 | 6800 | -0%
Bespoke | Number of new parking spaces | n of | 319 | 319 | 319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 319 | -0%
Bespoke | Additional Learners (FE) | n of | 1000 | 0 | 0 | 0 | 0 | 50 | 50 | 100 | 0 | 0 | 50 | 50 | 100 | 800 | 1000 | -0%
Bespoke | Additional Learners (HE) | n of | 1000 | 0 | 0 | 0 | 0 | 50 | 50 | 100 | 0 | 0 | 50 | 50 | 100 | 800 | 1000 | -0%
Bespoke | Additional Learners (CPD) | n of | 1000 | 0 | 0 | 0 | 0 | 50 | 50 | 100 | 0 | 0 | 50 | 50 | 100 | 800 | 1000 | -0%
Bespoke | Learners moving into Healthcare from other sectors | n of | 950 | 0 | 0 | 0 | 0 | 25 | 25 | 50 | 0 | 0 | 25 | 25 | 50 | 850 | 950 | -0%
Bespoke | Local employment (NHS workers living within 10 mile radious) | n of | 500 | 0 | 0 | 0 | 0 | 50 | 50 | 100 | 0 | 0 | 50 | 50 | 100 | 300 | 500 | -0%
Bespoke | Increase in the amount of diversity of commercial floorspace (sqm) | sqm | 750 | 750 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | -0%
Bespoke | Increase in existing visits (%) | % | 20 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 3 | 3 | 13 | 20 | -0%
Bespoke | Increase in dwell time (%) | % | 7 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 4 | 7 | -0%
Bespoke | Increase in number of trading units | n of | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | -0%
Bespoke | Number of new awnings & food hall | n of | 1 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 600%
Bespoke | Increase in amount of shared innovation facilities (%) | % | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | -0%
Bespoke | Increase in amount of new specialist technology equipment (%) | % | 20 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | -0%
Bespoke | Increase in uptake of digital/technical apprenticeships (%) | % | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | -0%
Bespoke | Increase in the share of young people & adults who have the relevant skills for employment & entrepreneurship (%) | % | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | -0%
Bespoke | Increase in new business start ups (%) | % | 20 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | -0%
Bespoke | Increase in business scale ups (%) | % | 20 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | -0%
Bespoke | Increase in no of visitors to arts, culture & heritage events | n of | 20 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | -0%
Bespoke | Rehabilitated land m2 | sqm | 32374 | 0 | 0 | 0 | 0 | 0 | 32374 | 32374 | 0 | 0 | 0 | 0 | 0 | 0 | 32374 | -0%
Bespoke | Improved parking spaces | n of | 406 | 0 | 0 | 0 | 0 | 0 | 406 | 406 | 0 | 0 | 0 | 0 | 0 | 0 | 406 | -0%
Bespoke | Sites cleared | n of | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | -0%
Bespoke | Additional enterprises with broadband access | n of | 15 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | -0%
Bespoke | Non domestic buildings with green retrofit | n of | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -0%
Bespoke | Office Space renovated/improved | sqm | 5574 | 0 | 0 | 0 | 0 | 0 | 6038 | 6038 | 0 | 0 | 0 | 0 | 0 | 0 | 6038 | 8.324%
Bespoke | Potential entrepreneurs assisted | n of | 20 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 0 | 0 | 0 | 13 | 13 | 0 | 20 | -0%
Bespoke | Closer collaboration with employers | n of | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | -0%
Bespoke | Increase in capacity and accessibility to new/improved facilities | % | 15 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | -0%
Bespoke | m2 of heritage buildings renovated/restored | sqm | 1962 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | -98.98%
Bespoke | Improved perception of place (%) visitors, businesses, residents | % | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -100%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
PF-USER_BESPOKE-OUTPUTS-END
Note on F20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: tbc

## Outcomes
Outcomes
What have you delivered, and what is forecast to be delivered?
Tell us about the outputs you are delivering and the outcomes these are achieving, or expected to achieve. Provide this at portfolio level by intervention theme. Investment themes have been developed to help MHCLG evaluate how our funds are helping to achieve Levelling Up. Investment themes are designed to organise outputs and outcomes by the objective of the project rather than the nature of the activities being undertaken. This is because similar projects can have different objectives and different activities can achieve the same result. For example, road improvements can facilitate development by linking a site to the road network or strengthen the service economy by making it easier to access a visitor attraction. When selecting an investment theme, think about the main long term objective of delivering the output or outcome.
Description of investment themes
Intervention theme | Description
Improving quality of life for residents | Projects where the principal aim is to improve the quality of life of residents by improving the quality of local public services and associated infrastructure. Projects funded under this heading are diverse: including improvements to educational, health, leisure and community facilities, environmental amenities (for example, parks), investments in new or improved social housing stock, and provisioning of cycling and walking infrastructure.
Strengthening the local service economy | Projects aiming to support economic regeneration via stimulating greater levels of consumer spending in local economies. These include investments in culture or heritage assets that serve as visitor attractions, investments in the public realm (for example, town centre improvement projects or enhancements to other infrastructure to improve the visitor experience), and provisioning of new or improved retail floorspace.
Unlocking commercial, industrial and residential development | Projects aiming to support economic regeneration or accommodate economic growth by unlocking or enabling the development of brownfield or greenfield for employment or residential uses. These projects would include direct investments in property development, investments in land reclamation or remediation, as well as the provisioning of site services (including access roads) to enable their onward development.
Enhancing regional and subregional connectivity | Projects aiming to improve connectivity between areas by creating new routes between areas, reducing congestion, or otherwise reducing journey times. These include direct investments in new or improved road or rail links, as well as enhancements to other forms of public transport. Active travel projects, such as new or improved cyclepaths and walkways should be categorised as improving quality of life.
Employment and education | Projects that aim to improve the level of skills attainment by increasing access to education, training and career opportunities. These include support for businesses to create jobs, new or improved education, community, and leisure facilities to be used for learning and developing skills.
Standard outcomes
PF-USER_STANDARD-OUTCOMES-START
Intervention theme | Outcome | Unit of measurement | Baseline outcome | Total cumulative outcomes to date |  | Financial year 2024 to 2025 |  |  |  |  | Financial year 2025 to 2026 |  |  |  |  | April 2026 and after | Grand total | Variance % (Between MR and Baseline)
|  |  |  | (Up to and including Mar 2024) | Total | (Apr to Jun) | (Jul to Sep) | (Oct to Dec) | (Jan to Mar) | Total | (Apr to Jun) | (Jul to Sep) | (Oct to Dec) | (Jan to Mar) | Total | Total
|  |  |  | Actual |  | Actual | Actual | Forecast | Forecast |  | Forecast | Forecast | Forecast | Forecast
Enhancing subregional and regional connectivity | Footfall | n of | 1220007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -100%
Enhancing subregional and regional connectivity | Cycle flow | n of | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Enhancing subregional and regional connectivity | Pedestrian flow | n of | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Enhancing subregional and regional connectivity | Vehicle flow | n of | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Enhancing subregional and regional connectivity | Public transport reliability | % | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Enhancing subregional and regional connectivity | Change in perceived/experienced accessibility | % | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Unlocking and enabling industrial commercial and residential development | Percentage of adults who are satisfied with their local area as a place to live | % | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Unlocking and enabling industrial commercial and residential development | Number of major commercial planning applications granted | n of | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Unlocking and enabling industrial commercial and residential development | Number of minor commercial planning applications granted | n of | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Strengthening the visitor and local service economy | Number of people using a new/improved public facility | n of | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Strengthening the visitor and local service economy | Vacancy rate of commercial units | % | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Strengthening the visitor and local service economy | Percentage of residents who report feeling safe in their local area | % | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Strengthening the visitor and local service economy | Number of crimes reported | n of | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Strengthening the visitor and local service economy | Number of anti-social behaviour crimes recorded | n of | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Strengthening the visitor and local service economy | Number of day visitors | n of | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Strengthening the visitor and local service economy | Total consumer spending at cultural venues | £ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Strengthening the visitor and local service economy | Number of visitors to cultural venues | n of | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Strengthening the visitor and local service economy | Number of cultural events | n of | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Strengthening the visitor and local service economy | Audience numbers for cultural events | n of | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Improving the quality of life of residents | Change in number of properties better protected from flooding and coastal erosion | % | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
PF-USER_STANDARD-OUTCOMES-END
Bespoke outcomes
PF-USER_BESPOKE-OUTCOMES-START
Intervention theme | Outcome | Unit of measurement | Baseline outcome | Total cumulative outcomes to date |  | Financial year 2024 to 2025 |  |  |  |  | Financial year 2025 to 2026 |  |  |  |  | April 2026 and after | Grand total | Variance % (Between MR and Baseline)
|  |  |  | (Up to and including Mar 2024) | Total | (Apr to Jun) | (Jul to Sep) | (Oct to Dec) | (Jan to Mar) | Total | (Apr to Jun) | (Jul to Sep) | (Oct to Dec) | (Jan to Mar) | Total | Total
|  |  |  | Actual |  | Actual | Actual | Forecast | Forecast |  | Forecast | Forecast | Forecast | Forecast
Bespoke | Travel times in corridors of interest | % | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 10 | 0%
Bespoke | Number of enterprises receiving non financial support | n of | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 0%
Bespoke | No of births of new enterprises | n of | 33 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 5 | 5 | 27 | 33 | -0%
Bespoke | Average occupany rates work spaces (5) | n of | 515 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 0 | 0 | 0 | 50 | 50 | 435 | 515 | -0%
Bespoke | (%) of adults satisfied with their area | % | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 20 | 30 | -0%
Bespoke | (%) of visitors likely to recommend the town | % | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | -0%
Bespoke | No of people using an improved/new public facility (%) | n of | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 20 | -0%
Bespoke | (%) of customers or visitors who report a positive experience | % | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | -0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
Please select an option | Please select an option |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0%
PF-USER_BESPOKE-OUTCOMES-END

## Finances
Finances
Portfolio-level finances
The following questions refer to the current financial year that you are reporting against.
PF-USER_CURRENT-UNDERSPEND-START
Current underspend
What is the current underspend for this financial year?
Enter numbers only
100
PF-USER_CURRENT-UNDERSPEND-END
Forecast and actual spend - Capital
PF-USER_FORECAST-AND-ACTUAL-SPEND-CAPITAL-START
Type of spend | Total cumulative actuals to date |  | Financial year 2024 to 2025 |  |  |  |  | Financial year 2025 to 2026 |  |  |  |  | Grand total
| (Up to and including Mar 2024) | Total | (Apr to Jun) | (Jul to Sep) | (Oct to Dec) | (Jan to Mar) | Total | (Apr to Jun) | (Jul to Sep) | (Oct to Dec) | (Jan to Mar) | Total
| Actual |  | Actual | Actual | Forecast | Forecast |  | Forecast | Forecast | Forecast | Forecast
How much of your forecast is contractually committed (this includes actual expenditure)? | 6898813 | 6898813 | f | 1030000 | 362422.5 | 255457.53 | 1647880.03 | 740800.71 | 336991 | 100000 | 0 | 1177791.71 | 9724484.74
How much of your forecast is not contractually committed? | 0 | 0 | 0 | 0 | 0 | 61715.93 | 61715.93 | 0 | 0 | 0 | 2360671.59 | 2360671.59 | 2422387.52
Freedom and flexibilities spend | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total MHCLG spend (inc. F&F) | 6898813 | 6898813 | 0 | 1030000 | 362422.5 | 317173.46 | 1709595.96 | 740800.71 | 336991 | 100000 | 2360671.59 | 3538463.3 | 12146872.26
Secured match funding spend (this includes actual match funding) | 5243075 | 5243075 | 8234419.9012 | 8234419.9012 | 8234419.9012 | 8234419.9012 | 32937679.6049 | 193250.875 | 193250.875 | 193250.875 | 193251.875 | 773004.5 | 38953759.1049
Unsecured match funding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total match | 5243075 | 5243075 | 8234419.9012 | 8234419.9012 | 8234419.9012 | 8234419.9012 | 32937679.6049 | 193250.875 | 193250.875 | 193250.875 | 193251.875 | 773004.5 | 38953759.1049
Total | 12141888 | 12141888 | 8234419.9012 | 9264419.9012 | 8596842.4012 | 8551593.3612 | 34647275.5649 | 934051.585 | 530241.875 | 293250.875 | 2553923.465 | 4311467.8 | 51100631.3649
PF-USER_FORECAST-AND-ACTUAL-SPEND-CAPITAL-END
Forecast and actual spend - Revenue
PF-USER_FORECAST-AND-ACTUAL-SPEND-REVENUE-START
Type of spend | Total cumulative actuals to date |  | Financial year 2024 to 2025 |  |  |  |  | Financial year 2025 to 2026 |  |  |  |  | Grand total
| (Up to and including Mar 2024) | Total | (Apr to Jun) | (Jul to Sep) | (Oct to Dec) | (Jan to Mar) | Total | (Apr to Jun) | (Jul to Sep) | (Oct to Dec) | (Jan to Mar) | Total
| Actual |  | Actual | Actual | Forecast | Forecast |  | Forecast | Forecast | Forecast | Forecast
How much of your forecast is contractually committed (this includes actual expenditure)? | 6898813 | 6898813 | 2950678.83 | 1030000 | 362422.5 | 255457.53 | 4598558.86 | 740800.71 | 336991 | 100000 | 0 | 1177791.71 | 12675163.57
How much of your forecast is not contractually committed? | 0 | 0 | 0 | 0 | 0 | 61715.93 | 61715.93 | 0 | 0 | 0 | 2360671.59 | 2360671.59 | 2422387.52
Freedom and flexibilities spend | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | g | 0 | 0 | 0 | 0
Total MHCLG spend (inc. F&F) | 6898813 | 6898813 | 2950678.83 | 1030000 | 362422.5 | 317173.46 | 4660274.79 | 740800.71 | 336991 | 100000 | 2360671.59 | 3538463.3 | 15097551.09
Secured match funding spend (this includes actual match funding) | 5243075 | 5243075 | 8234419.9012 | 8234419.9012 | 8234419.9012 | 8234419.9012 | 32937679.6049 | 193250.875 | 193250.875 | 193250.875 | 193251.875 | 773004.5 | 38953759.1049
Unsecured match funding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total match | 5243075 | 5243075 | 8234419.9012 | 8234419.9012 | 8234419.9012 | 8234419.9012 | 32937679.6049 | 193250.875 | 193250.875 | 193250.875 | 193251.875 | 773004.5 | 38953759.1049
Total | 12141888 | 12141888 | 11185098.7312 | 9264419.9012 | 8596842.4012 | 8551593.3612 | 37597954.3949 | 934051.585 | 530241.875 | 293250.875 | 2553923.465 | 4311467.8 | 54051310.1949
PF-USER_FORECAST-AND-ACTUAL-SPEND-REVENUE-END
PF-USER_UNCOMMITTED-FUNDING-PLAN-START
Uncommitted funding plan
What is your plan for using any uncommitted funding?
Please set out how uncommitted funding will be used, indicating when funds will become committed. This should cover your underspend as detailed above and remaining uncommitted allocation. Please write "N/A" if all of your funding is committed.
As q 4
500 words suggested | [5 empty] | PF-USER_UNCOMMITTED-FUNDING-PLAN-END
PF-USER_SUMMARY-OF-CHANGES-BELOW-CHANGE-REQUEST-THRESHOLD-START
Summary of changes below change request threshold
What changes have you made, or plan to make, that are below the change request threshold?
The threshold is £5m or more moved between projects or intervention themes. Changes below the threshold could include: reallocating funding between projects; making an adjustment to a project and delivering different outputs/outcomes; scrapping a project; delivering a new project; or moving funding between geographical areas within the local authority.
The timeframe for the xxx project has been shifted from an end date of March 2024 into 2024/25. Priority will be given to spending the FHSF allocation first and using matchfunding to fund later stages of the project. FHSF will be used on Phase One of the project. The outputs remain the same.
500 words suggested | [5 empty] | PF-USER_SUMMARY-OF-CHANGES-BELOW-CHANGE-REQUEST-THRESHOLD-END
Project finance changes
Only include changes where the amount moved falls below the change request threshold.
PF-USER_PROJECT-FINANCE-CHANGES-START
Change number | Project funding moved from |  | Intervention theme moved from |  | Project funding moved to |  | Intervention theme moved to |  | Amount moved | What changes have you made / or are planning to make? (100 words max) |  | Reason for change (100 words max) |  | Actual, forecast or cancelled | Reporting period change takes place
1 | PF-ANO-008: Streets for All - Anon |  | Enhancing subregional and regional connectivity |  | PF-ANO-008: Streets for All - Anon |  | Enhancing subregional and regional connectivity |  | 1637422 | Change in timescale of delivery to 2024/25 |  | Finalising design principles |  | Forecast | Q3 2024/25: Oct 2024 - Dec 2024
| Please select an option |  | Please select an option |  | Please select an option |  | Please select an option | [6 empty] | Please select an option | Please select an option
| Please select an option |  | Please select an option |  | Please select an option |  | Please select an option | [6 empty] | Please select an option | Please select an option
| Please select an option |  | Please select an option |  | Please select an option |  | Please select an option | [6 empty] | Please select an option | Please select an option
| Please select an option |  | Please select an option |  | Please select an option |  | Please select an option | [6 empty] | Please select an option | Please select an option
| Please select an option |  | Please select an option |  | Please select an option |  | Please select an option | [6 empty] | Please select an option | Please select an option
| Please select an option |  | Please select an option |  | Please select an option |  | Please select an option | [6 empty] | Please select an option | Please select an option
| Please select an option |  | Please select an option |  | Please select an option |  | Please select an option | [6 empty] | Please select an option | Please select an option
| Please select an option |  | Please select an option |  | Please select an option |  | Please select an option | [6 empty] | Please select an option | Please select an option
| Please select an option |  | Please select an option |  | Please select an option |  | Please select an option | [6 empty] | Please select an option | Please select an option
| Please select an option |  | Please select an option |  | Please select an option |  | Please select an option | [6 empty] | Please select an option | Please select an option
| Please select an option |  | Please select an option |  | Please select an option |  | Please select an option | [6 empty] | Please select an option | Please select an option
| Please select an option |  | Please select an option |  | Please select an option |  | Please select an option | [6 empty] | Please select an option | Please select an option
| Please select an option |  | Please select an option |  | Please select an option |  | Please select an option | [6 empty] | Please select an option | Please select an option
| Please select an option |  | Please select an option |  | Please select an option |  | Please select an option | [6 empty] | Please select an option | Please select an option
| Please select an option |  | Please select an option |  | Please select an option |  | Please select an option | [6 empty] | Please select an option | Please select an option
| Please select an option |  | Please select an option |  | Please select an option |  | Please select an option | [6 empty] | Please select an option | Please select an option
| Please select an option |  | Please select an option |  | Please select an option |  | Please select an option | [6 empty] | Please select an option | Please select an option
PF-USER_PROJECT-FINANCE-CHANGES-END
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The order of questions in this sheet feels off. In Mural we ask for the committed and forecast spend first, then follow with uncommitted, underspend, credible plan and changes. Reply: Does it matter to the user what order they fill these out in? Or do some topics / data points logically follow on from others?

## Risks
Risks
What are the main risks across your portfolio? Please enter five.
If you have resolved a risk since your last submission, log it here as closed and tell us how well your mitigations worked. We use this information to see how problems get solved, so we can share that knowledge with others.
PF-USER_RISKS-START
Risk name | Category | Description | Pre-mitigated likelihood score | Pre-mitigated impact score | Pre-mitigated total risk score | Mitigations | Post-mitigated likelihood score | Post-mitigated impact score | Post-mitigated total risk score
| Select risk categories applicable to the portfolio. | Explain what might go wrong and why, and what the outcome would be if it did. (100 words maximum) | What is the probability of this happening, based on mitigations already in place? | To what extent would this affect delivery, based on mitigations already in place? | We calculate this by multiplying the likelihood score with the impact score. | Explain the mitigations you had, have, or plan to have in place to manage the risk. (100 words maximum) | What level of confidence do you have that the risk has now been mitigated? | To what extent did the mitigations ensure that delivery was not affected? | We calculate this by multiplying the likelihood score with the impact score.
Economic Downturn | Commercial or procurement risks | Most projects in the portfolio are either completed or nearing completion. Therefore risks are around delivering outputs an outcomes. An economic downturn may adversley impact trading conditions and take up of facilties provided by the projects. | 2 - Low | 3 - Medium | 6 | Management of facilities will include forward planning to mitigate impact of economic change | 2 - Low | 2 - Low | 4
Government policy change | Political sensitivity | A change in government and policy shift may impact achievement of outputs/outcomes | 4 - High | 1 - Very Low | 4 | Management of facilities will include forward planning to mitigate impact of political change | 1 - Very Low | 2 - Low | 2
Construction cost pressures | Commercial or procurement risks | A return of inflation will impact materials costs | 2 - Low | 4 - High | 8 | Most projects are sufficently advacned in procurement to have secured firm costs | 2 - Low | 2 - Low | 4
Local policy shift | Political sensitivity | A change in the political composition Council may affext policy and priorities | 3 - Medium | 3 - Medium | 9 | Incoming elected members are briefed about the projects and status of projects is advanced to make variation unlikely | 3 - Medium | 1 - Very Low | 3
Shift in priority of partner | Political sensitivity | The remaining project is being delivered in partnership with a third party whose priority may change before the project si completed | 1 - Very Low | 3 - Medium | 3 | Project design is well advanced and partner is committed | 1 - Very Low | 2 - Low | 2
PF-USER_RISKS-END

## Sign off
Sign off
Please ensure this document is signed by the Section 151 Officer or Chief Finance Officer. No other signatories will be accepted.
Section 151 Officer or Chief Finance Officer
I confirm that: • the information in this document is accurate • all significant issues affecting deliverability of the project have been disclosed • the Board has seen this document before submission
PF-USER_SIGNATORY-NAME-START
Signatory name
Tester McTestface
PF-USER_SIGNATORY-NAME-END
PF-USER_SIGNATORY-ROLE-START
Signatory role
S151 Officer
PF-USER_SIGNATORY-ROLE-END
PF-USER_SIGNATURE-IMAGE-START
Signature image
This must be an image
PF-USER_SIGNATURE-IMAGE-END
PF-USER_SIGNATURE-DATE-START
Signature date
Enter following this format: dd/mm/yyyy
2024-09-20
PF-USER_SIGNATURE-DATE-END
Council Leader | [8 empty] | Enumeration Values
Name | [8 empty] | <Select>
Role | [8 empty] | Yes
Confirm information provided is accurate | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No
Date (dd/mm/yyyy)

## Dropdown Values
PF-CONTROL_GLOBAL-DROPDOWN-PLACEHOLDER-START
Global dropdown placeholder
Please select an option
PF-CONTROL_GLOBAL-DROPDOWN-PLACEHOLDER-END
PF-CONTROL_REPORTING-PERIOD-START
Reporting period
Please select an option
Q4 2023/24: Jan 2024 - Mar 2024
Q1 2024/25: Apr 2024 - Jun 2024
Q2 2024/25: Jul 2024 - Sep 2024
Q3 2024/25: Oct 2024 - Dec 2024
Q4 2024/25: Jan 2025 - Mar 2025
Q1 2025/26: Apr 2025 - Jun 2025
Q2 2025/26: Jul 2025 - Sep 2025
Q3 2025/26: Oct 2025 - Dec 2025
Q4 2025/26: Jan 2026 - Mar 2026
PF-CONTROL_REPORTING-PERIOD-END
PF-CONTROL_ORGANISATION-NAME-START
Organisation name
Please select an option
Test Council
PF-CONTROL_ORGANISATION-NAME-END
PF-CONTROL_PROJECT-STATUS-START
Project status
Please select an option
Not started
In progress
On hold
Project cancelled
Project complete
PF-CONTROL_PROJECT-STATUS-END
PF-CONTROL_RAG-RATING-START
Progress RAG rating
Please select an option
Green
Amber/Green
Amber
Amber/Red
Red
PF-CONTROL_RAG-RATING-END
PF-CONTROL_STANDARD-OUTPUTS-START
Standard output | UoM | Intervention theme
Please select an option | #N/A
Amount of existing hospitality space improved | sqm | Strengthening the visitor and local service economy
Amount of existing parks/greenspace/outdoor improved | sqm | Improving the quality of life of residents
Amount of existing retail space improved | sqm | Strengthening the visitor and local service economy
Amount of floor space repurposed (residential, commercial, retail) | sqm | Unlocking and enabling industrial commercial and residential development
Amount of land made wheelchair accessible/step free | sqm | Enhancing sub-regional and regional connectivity
Amount of new educational space created | sqm | Employment and education
Amount of new hospitality space created | sqm | Strengthening the visitor and local service economy
Amount of new parks/greenspace/outdoor space | sqm | Improving the quality of life of residents
Amount of new retail space created | sqm | Strengthening the visitor and local service economy
Amount of public realm improved | sqm | Strengthening the visitor and local service economy
Amount of rehabilitated land | sqm | Unlocking and enabling industrial commercial and residential development
n of full-time equivalent (FTE) permanent jobs created directly through the projects | n of | Employment and education
n of full-time equivalent (FTE) permanent jobs facilitated directly through the projects | n of | Employment and education
n of full-time equivalent (FTE) permanent jobs safeguarded directly through the projects | n of | Employment and education
n of temporary FT jobs supported during project implementation | n of | Employment and education
Number of alternative fuel charging/re-fuelling points | n of | Enhancing sub-regional and regional connectivity
Number of dilapidated buildings improved OR Number of derelict buildings refurbished | n of | Unlocking and enabling industrial commercial and residential development
Number of heritage buildings renovated/restored OR Number of buildings renovated/restored | n of | Strengthening the visitor and local service economy
Number of improved community/sports centres | n of | Strengthening the visitor and local service economy
Number of improved cultural facilities | n of | Strengthening the visitor and local service economy
Number of local events or activities supported | n of | Strengthening the visitor and local service economy
Number of neighbourhood improvements undertaken | n of | Strengthening the visitor and local service economy
Number of new community/sports centres | n of | Strengthening the visitor and local service economy
Number of new cultural facilities | n of | Strengthening the visitor and local service economy
Number of properties better protected from flooding and coastal erosion | n of | Improving the quality of life of residents
Number of public amenities/facilities created | n of | Strengthening the visitor and local service economy
Number of public amenities/facilities improved | n of | Strengthening the visitor and local service economy
Number of trees planted OR Number of new trees planted | n of | Improving the quality of life of residents
Total length of improved cycle ways | km | Enhancing sub-regional and regional connectivity
Total length of new cycle ways | km | Enhancing sub-regional and regional connectivity
Total length of new pedestrian paths | km | Enhancing sub-regional and regional connectivity
Total length of newly built roads | km | Enhancing sub-regional and regional connectivity
Total length of pedestrian paths improved | km | Enhancing sub-regional and regional connectivity
Total length of resurfaced/improved road | km | Enhancing sub-regional and regional connectivity
PF-CONTROL_STANDARD-OUTPUTS-END
PF-CONTROL_STANDARD-OUTCOMES-START
Standard outcome | UoM | Intervention theme
Please select an option | #N/A | #N/A
Audience numbers for cultural events | n of | Strengthening the visitor and local service economy
Change in number of properties better protected from flooding and coastal erosion | % | Improving the quality of life of residents
Change in perceived/experienced accessibility | % | Enhancing sub-regional and regional connectivity
Cycle flow | n of | Enhancing sub-regional and regional connectivity
Footfall | n of | Enhancing sub-regional and regional connectivity
Number of anti-social behaviour crimes recorded | n of | Strengthening the visitor and local service economy
Number of anti-social behaviour crimes recorded | n of | Improving the quality of life of residents
Number of crimes reported | n of | Strengthening the visitor and local service economy
Number of crimes reported | n of | Improving the quality of life of residents
Number of cultural events | n of | Strengthening the visitor and local service economy
Number of day visitors | n of | Strengthening the visitor and local service economy
Number of major commercial planning applications granted | n of | Unlocking and enabling industrial commercial and residential development
Number of minor commercial planning applications granted | n of | Unlocking and enabling industrial commercial and residential development
Number of people using a new/improved public facility | n of | Strengthening the visitor and local service economy
Number of visitors to cultural venues | n of | Strengthening the visitor and local service economy
Pedestrian flow | n of | Enhancing sub-regional and regional connectivity
Percentage of adults who are satisfied with their local area as a place to live | % | Unlocking and enabling industrial commercial and residential development
Percentage of residents who report feeling safe in their local area | % | Strengthening the visitor and local service economy
Percentage of residents who report feeling safe in their local area | % | Improving the quality of life of residents
Public transport reliability | % | Enhancing sub-regional and regional connectivity
Total consumer spending at cultural venues | £ | Strengthening the visitor and local service economy
Vacancy rate of commercial units | % | Strengthening the visitor and local service economy
Vehicle flow | n of | Enhancing sub-regional and regional connectivity
PF-CONTROL_STANDARD-OUTCOMES-END
PF-CONTROL_UNIT-OF-MEASUREMENT-START
Unit of measurement
Please select an option
km
n of
sqm
%
£
PF-CONTROL_UNIT-OF-MEASUREMENT-END
PF-CONTROL_INTERVENTION-THEME-START
Intervention theme
Please select an option
Employment and education
Enhancing subregional and regional connectivity
Improving the quality of life of residents
Strengthening the visitor and local service economy
Unlocking and enabling industrial commercial and residential development
PF-CONTROL_INTERVENTION-THEME-END
PF-CONTROL_INTERVENTION-THEME-BESPOKE-START
Bespoke intervention theme
Please select an option
Bespoke
PF-CONTROL_INTERVENTION-THEME-BESPOKE-END
PF-CONTROL_CREDIBLE-PLAN-START
Credible plan yes or no
Please select an option
Yes
No
PF-CONTROL_CREDIBLE-PLAN-END
PF-CONTROL_ACTUAL-FORECAST-CANCELLED-START
Actual, forecast or cancelled
Please select an option
Actual
Forecast
Cancelled
PF-CONTROL_ACTUAL-FORECAST-CANCELLED-END
PF-CONTROL_RISK-CATEGORY-START
Risk category
Please select an option
Arm’s length body risks
Commercial or procurement risks
Delivery Partner
Financial flexibility
Financial risks
Governance risks
Legal, regulatory or compliance risks
Local government risks
Operational process or control risks
People risks
Planning Permission / other consents
Political sensitivity
Procurement / contracting
Programme or project delivery risks
Reputational Risk
Resilience risks
Resource & Expertise
Security risks
Slippage
Strategy risks
Subsidy Control
System or IT infrastructure risks
Other
PF-CONTROL_RISK-CATEGORY-END
PF-CONTROL_RISK-SCORE-START
Risk score
Please select an option
5 - Very High
4 - High
3 - Medium
2 - Low
1 - Very Low
PF-CONTROL_RISK-SCORE-END

## Project Details (hidden)
PF-CONTROL_PROJECT-DETAILS-START
Local Authority | Reference | Project name | Status | Full name
Test Council | PF-ANO-001 | Anon Innovation Hub | Active | PF-ANO-001: Anon Innovation Hub
Test Council | PF-ANO-002 | Anon Market Upgrades | Active | PF-ANO-002: Anon Market Upgrades
Test Council | PF-ANO-003 | Anon Library & Museum Upgrade | Active | PF-ANO-003: Anon Library & Museum Upgrade
Test Council | PF-ANO-004 | Public Realm Improvements | Active | PF-ANO-004: Public Realm Improvements
Test Council | PF-ANO-005 | Accelerated Funding £1 million Public Realm Improvements | Active | PF-ANO-005: Accelerated Funding £1 million Public Realm Improvements
Test Council | PF-ANO-006 | Anon Market Precinct | Active | PF-ANO-006: Anon Market Precinct
Test Council | PF-ANO-007 | Anon Leisure Centre Expansion | Active | PF-ANO-007: Anon Leisure Centre Expansion
Test Council | PF-ANO-008 | Streets for All - Anon | Active | PF-ANO-008: Streets for All - Anon
Test Council | PF-ANO-009 | Anon College of Medical Science | Active | PF-ANO-009: Anon College of Medical Science
PF-CONTROL_PROJECT-DETAILS-END

## ITValues (hidden)
Standard Outputs |  |  |  |  | Standard Outcomes
Ensure the named ranges for the Outputs are set to the Scope of the Outputs tab (not workbook). Sames for Outcomes - ensure scope is Outcomes tab, not Workbook)
Ensure the named range has the name of the theme WITH NO SPACES e.g. "employmentandeducation". These values must match exactly the values for intervention themes that the user selects on the form
Strengthening the visitor and local service economy | Employment and education | Improving the quality of life of residents | Unlocking and enabling industrial commercial and residential development | Enhancing subregional and regional connectivity | Strengthening the visitor and local service economy | Employment and education | Improving the quality of life of residents | Unlocking and enabling industrial commercial and residential development | Enhancing subregional and regional connectivity
Amount of existing hospitality space improved | Amount of new educational space created | Amount of existing parks/greenspace/outdoor improved | Amount of floor space repurposed (residential, commercial, retail) | Amount of land made wheelchair accessible/step free | Audience numbers for cultural events | There are no options to select | Change in number of properties better protected from flooding and coastal erosion | Number of major commercial planning applications granted | Change in perceived/experienced accessibility
Amount of existing retail space improved | n of full-time equivalent (FTE) permanent jobs created directly through the projects | Amount of new parks/greenspace/outdoor space | Amount of rehabilitated land | Number of alternative fuel charging/re-fuelling points | Number of anti-social behaviour crimes recorded |  | Number of anti-social behaviour crimes recorded | Number of minor commercial planning applications granted | Cycle flow
Amount of new hospitality space created | n of full-time equivalent (FTE) permanent jobs facilitated directly through the projects | Number of properties better protected from flooding and coastal erosion | Number of dilapidated buildings improved OR Number of derelict buildings refurbished | Total length of improved cycle ways | Number of crimes reported |  | Number of crimes reported | Percentage of adults who are satisfied with their local area as a place to live | Footfall
Amount of new retail space created | n of full-time equivalent (FTE) permanent jobs safeguarded directly through the projects | Number of trees planted OR Number of new trees planted |  | Total length of new cycle ways | Number of cultural events |  | Percentage of residents who report feeling safe in their local area |  | Pedestrian flow
Amount of public realm improved | n of temporary FT jobs supported during project implementation |  |  | Total length of new pedestrian paths | Number of day visitors |  |  |  | Public transport reliability
Number of heritage buildings renovated/restored OR Number of buildings renovated/restored |  |  |  | Total length of newly built roads | Number of people using a new/improved public facility |  |  |  | Vehicle flow
Number of improved community/sports centres |  |  |  | Total length of pedestrian paths improved | Number of visitors to cultural venues
Number of improved cultural facilities |  |  |  | Total length of resurfaced/improved road | Percentage of residents who report feeling safe in their local area
Number of local events or activities supported |  |  |  |  | Total consumer spending at cultural venues
Number of neighbourhood improvements undertaken |  |  |  |  | Vacancy rate of commercial units
Number of new community/sports centres
Number of new cultural facilities
Number of public amenities/facilities created
Number of public amenities/facilities improved

## Bespoke Outputs (hidden)
Selected LA in Admin tab:
Test Council
PF-CONTROL_BESPOKE-OUTPUTS-START
Bespoke output | UoM | Local Authority | Output | UoM | Intervention theme
Please select an option | #N/A | Test Council | Please select an option | #N/A | Bespoke
Amount of new office space (m2) | sqm | Test Council | Amount of new office space (m2) | sqm | Bespoke
Amount of capacity of new or improved training or education facilities (people) | n of | Test Council | Amount of capacity of new or improved training or education facilities (people) | n of | Bespoke
Amount of public realm created (sqm) | sqm | Test Council | Amount of public realm created (sqm) | sqm | Bespoke
% increase in participation | % | Test Council | % increase in participation | % | Bespoke
% increase in membership | % | Test Council | % increase in membership | % | Bespoke
% increase in Health Pathway referrals | % | Test Council | % increase in Health Pathway referrals | % | Bespoke
Number of residential units | n of | Test Council | Number of residential units | n of | Bespoke
Amount of new healthcare facilities sqm | sqm | Test Council | Amount of new healthcare facilities sqm | sqm | Bespoke
Number of new parking spaces | n of | Test Council | Number of new parking spaces | n of | Bespoke
Additional Learners (FE) | n of | Test Council | Additional Learners (FE) | n of | Bespoke
Additional Learners (HE) | n of | Test Council | Additional Learners (HE) | n of | Bespoke
Additional Learners (CPD) | n of | Test Council | Additional Learners (CPD) | n of | Bespoke
Learners moving into Healthcare from other sectors | n of | Test Council | Learners moving into Healthcare from other sectors | n of | Bespoke
Local employment (NHS workers living within 10 mile radious) | n of | Test Council | Local employment (NHS workers living within 10 mile radious) | n of | Bespoke
Number of improved community/sports centres | n of | Test Council | Number of improved community/sports centres | n of | Bespoke
Increase in the amount of diversity of commercial floorspace (sqm) | sqm | Test Council | Increase in the amount of diversity of commercial floorspace (sqm) | sqm | Bespoke
Increase in existing visits (%) | % | Test Council | Increase in existing visits (%) | % | Bespoke
Increase in dwell time (%) | % | Test Council | Increase in dwell time (%) | % | Bespoke
Increase in number of trading units | n of | Test Council | Increase in number of trading units | n of | Bespoke
Number of new awnings & food hall | n of | Test Council | Number of new awnings & food hall | n of | Bespoke
Increase in amount of shared innovation facilities (%) | % | Test Council | Increase in amount of shared innovation facilities (%) | % | Bespoke
Increase in amount of new specialist technology equipment (%) | % | Test Council | Increase in amount of new specialist technology equipment (%) | % | Bespoke
Increase in uptake of digital/technical apprenticeships (%) | % | Test Council | Increase in uptake of digital/technical apprenticeships (%) | % | Bespoke
Increase in the share of young people & adults who have the relevant skills for employment & entrepreneurship (%) | % | Test Council | Increase in the share of young people & adults who have the relevant skills for employment & entrepreneurship (%) | % | Bespoke
Increase in new business start ups (%) | % | Test Council | Increase in new business start ups (%) | % | Bespoke
Increase in business scale ups (%) | % | Test Council | Increase in business scale ups (%) | % | Bespoke
m2 of heritage buildings renovated/restored | sqm | Test Council | m2 of heritage buildings renovated/restored | sqm | Bespoke
Increase in no of visitors to arts, culture & heritage events | n of | Test Council | Increase in no of visitors to arts, culture & heritage events | n of | Bespoke
Improved perception of place (%) visitors, businesses, residents | % | Test Council | Improved perception of place (%) visitors, businesses, residents | % | Bespoke
Rehabilitated land m2 | sqm | Test Council | Rehabilitated land m2 | sqm | Bespoke
Improved parking spaces | n of | Test Council | Improved parking spaces | n of | Bespoke
Sites cleared | n of | Test Council | Sites cleared | n of | Bespoke
Additional enterprises with broadband access | n of | Test Council | Additional enterprises with broadband access | n of | Bespoke
Non domestic buildings with green retrofit | n of | Test Council | Non domestic buildings with green retrofit | n of | Bespoke
Office Space renovated/improved | sqm | Test Council | Office Space renovated/improved | sqm | Bespoke
Potential entrepreneurs assisted | n of | Test Council | Potential entrepreneurs assisted | n of | Bespoke
Closer collaboration with employers | n of | Test Council | Closer collaboration with employers | n of | Bespoke
Increase in capacity and accessibility to new/improved facilities | % | Test Council | Increase in capacity and accessibility to new/improved facilities | % | Bespoke
PF-CONTROL_BESPOKE-OUTPUTS-END

## Bespoke Outcomes (hidden)
Selected LA in Admin tab:
Test Council
PF-CONTROL_BESPOKE-OUTCOMES-START
Bespoke outcome | UoM | Local Authority | Outcome | UoM | Intervention theme
Please select an option | #N/A | Test Council | Please select an option | #N/A | Bespoke
Travel times in corridors of interest | % | Test Council | Travel times in corridors of interest | % | Bespoke
Number of enterprises receiving non financial support | n of | Test Council | Number of enterprises receiving non financial support | n of | Bespoke
No of births of new enterprises | n of | Test Council | No of births of new enterprises | n of | Bespoke
Average occupany rates work spaces (5) | n of | Test Council | Average occupany rates work spaces (5) | n of | Bespoke
(%) of adults satisfied with their area | % | Test Council | (%) of adults satisfied with their area | % | Bespoke
(%) of visitors likely to recommend the town | % | Test Council | (%) of visitors likely to recommend the town | % | Bespoke
No of people using an improved/new public facility (%) | n of | Test Council | No of people using an improved/new public facility (%) | n of | Bespoke
(%) of customers or visitors who report a positive experience | % | Test Council | (%) of customers or visitors who report a positive experience | % | Bespoke
PF-CONTROL_BESPOKE-OUTCOMES-END